## Macro planning V0.1
MACRO PLANNING V0.1
|  |  |  | Kick-Off | [6 empty] | Go live
| Committee 1 |  | Committee 2 | Directors Board |  |  | Committee 3 |  |  |  | Committee 4
August |  | September |  |  | October |  |  |  | November |  |  | December
Scoping Meeting
Preparation Phase
Design Phase
Build Phase
Unit Tests & Integrations Tests
UAT+ training
Data Migration
RSV

## Macro Planning V1
MACRO PLANNING V.1
Responsible of Document: Samira MHAMSA,
Author: Samira MHAMSA 22/09/2023
Validation:
Last update: Samira MHAMSA 29/09/2023 |  |  |  | Start | End | Duration | Phase | Vert. Position | Vert. Ligne
Proofread: Fanta GABY, 28/09/2023
|  |  |  | 2023-08-21 | 2023-09-01 | 14 | Scoping Meeting | -25 | -25
Tasks |  |  |  | 2023-09-04 | 2023-09-22 | 18 | Preparation Phase | -40 | -15
Start | End | Duration | Phase | 2023-09-25 | 2023-10-13 | 20 | Design Phase | -55 | -15
|  |  |  | 2023-10-16 | 2023-11-03 | 18 | Build Phase | -80 | -80
2023-08-21 | 2023-09-01 | 14 | Scoping Meeting | 2023-10-23 | 2023-11-03 | 14 | Unit Tests & Integrations Tests | -30 | -30
2023-09-04 | 2023-09-22 | 18 | Preparation Phase | 2023-11-06 | 2023-11-10 | 7 | Users Acceptance Tests | -45 | -15
2023-09-25 | 2023-10-13 | 20 | Design Phase | 2023-11-06 | 2023-11-10 | 7 | Training | -20 | -20
2023-10-16 | 2023-11-03 | 18 | Build Phase | 2023-11-06 | 2023-11-10 | 7 | Data Migration | -60 | -40
2023-10-23 | 2023-11-03 | 14 | Unit Tests & Integrations Tests | 2023-11-13 | 2023-11-24 | 14 | RVS | -75 | -15
2023-11-06 | 2023-11-10 | 7 | Users Acceptance Tests |  |  |  | Insérez les nouvelle lignes au-dessus de celle-ci
2023-11-06 | 2023-11-10 | 7 | Training
2023-11-06 | 2023-11-10 | 7 | Data Migration | Milestone
2023-11-13 | 2023-11-24 | 14 | RVS | Date |  |  | Milestone | Position
Insérez les nouvelle lignes au-dessus de celle-ci
|  |  |  | 2023-08-21 |  |  | START | 30
Milestone |  |  |  | 2023-09-12 |  |  | Pre-Copil | 10
Date |  |  | Milestone | 2023-09-20 |  |  | Copil | 15
|  |  |  | 2023-09-29 |  |  | Codir | 10
2023-08-21 |  |  | START | 2023-09-29 |  |  | KICK OFF 29/09/2023 | 30
2023-09-12 |  |  | Copil | 2023-10-11 |  |  | Pre-Copil | 20
2023-09-20 |  |  | Copil | 2023-10-20 |  |  | Copil | 25
2023-09-29 |  |  | Codir | 2023-11-21 |  |  | Forecast-Copil | 10
2023-09-29 |  |  | KICK OFF 29/09/2023 | 2023-11-22 |  |  | GO LIVE 22/11/2023 | 30
2023-10-11 |  |  | Pre-Copil |  |  |  | Insérez les nouvelle lignes au-dessus de celle-ci
2023-10-20 |  |  | Forecast-Copil
2023-11-21 |  |  | Forecast-Copil
2023-11-22 |  |  | GO LIVE 22/11/2023
Insérez les nouvelle lignes au-dessus de celle-ci
Formulas:
End = [Start]+[Duration]-3
Start = [End, row above]+3