## Planning
SIGMA 360 PROJECT | SALESFORCE/SALES CLOUD PROFESSIONAL EDITION
Open Project Gantt Diagram | ​Responsible of Document: 10/09/2023 Etienne BERNOULI, 16/10/2023 Samira MHAMSA, 13/11/2023 Elisa FAUCI
EKOVYA Project Tracker Open Project | Author: Elisa FAUCI, Samira MHAMSA 21/08/2023
Macro Planning | Last update: Samira MHAMSA 03/11/2023
TEAM CRM ALPHA | 2023 | Project Director: Philippe Bassot |  | Consultants Availability : 3 Full Days/Week | Post-Go Live period = 1% of project's time | Number of consultants: 8 | Materials needed: 8 computers + mouses + Internet connection (Account 78112. "Immobilisations corporelles") [Amortization] | Landscape : Virtual environnements : Playgrounds + Dev + QA + PreProd + Prod = 4 SF environments + playgrounds | Sales cloud Licences x 4 Professional edition (official) | Sales Cloud Licences x 1 Professional edition (IRL)
Color Legend
Done
Done and often actualized
Ongoing
Important - not started
Important - started
Not Mandatory
Canceled
PREPARATION PHASE | [74 empty] | Room for manoeuver
Month | [8 empty] | August | [34 empty] | October | [24 empty] | November | [11 empty] | December
Weeks | [6 empty] | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49
Dates |  |  |  |  | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 28/08/2028 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-02-10 | 2023-03-10 | 2023-04-10 | 2023-05-10 | 2023-06-10 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 16/10/2023 | 17/10/2023 | 18/10/2023 | 19/10/2023 | 20/10/2023 | 23/10/2023 | 24/10/2023 | 25/10/2023 | 26/10/2023 | 27/10/2023 | 30/10/2023 | 31/10/2023 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08
Tasks | Description | Document(s) | Level of Progress | Task Manager/Responsible | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Time Tracking | Recording work hours of the consultants of the team CRM Alpha for the project SIGMA360 Salesforce | EKOVYA Project Tracker Open Project | To be actualized in Real-Time | Etienne
Gantt Diagram | To be presented every Steering Comitee, with tasks and time allocation. | EKOVYA Project Tracker Open Project | To be actualized in Real-Time | Etienne
Macro Planning | / | S360-SAF-MACRO PLANNING-23Q3-TEAM-V.1.xlsx |  | Samira
Project planification | / | S360-SAF-DETAILED_ORGANIZATION-210923-TEAM-V1.docx |  | Etienne, collaborative | [5 empty] | Morning | [23 empty] | KICK OFF! | [37 empty] | GO LIVE!
Workshop/ First meeting/ Reception of needs | ????? | S360-SAF-REQUIREMENTS REVIEW-23Q3-OPEN-V1.docx | Done | Collaborative | [5 empty] | Morning | [23 empty] | KICK OFF! | [37 empty] | GO LIVE!
Landscape Definition | Common Playground (personal accounts), Dev (1 trailhead common account), QA (UAT) (1 trailhead playground account, 2 users), Training (no training), PreProd (no PreProd), Production (1 licence professional) | See case on the left | Done | Etienne | [8 empty] | Morning | COPIL | [6 empty] | PRE-COPIL | [6 empty] | COPIL | [5 empty] | KICK OFF! |  |  | PRE-COPIL | [13 empty] | COPIL
Requirements Review | How many workshops/days we need to integrate/harvest all requirements. | S360-SAF-REQUIREMENTS REVIEW-23Q4-OPEN-V1.1 | Done | Olivier/ Etienne | [8 empty] | Morning |  |  |  | Morning | Morning |  | Evening | [13 empty] | KICK OFF! | [37 empty] | GO LIVE!
Scoping | A meeting with the client to define the budget (BigBudget) and the limits of the project. Confidential information, organization charts. Reading between the lines. It's all about clearing the ground, getting as real a picture of the company as possible. | S360-SAF-SCOPING_NOTE-23Q3-OPEN-V1 | Done | Collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Ishikawa's diagram | Delimiting the scope of the project in relation to methods, environment, materials, management, manpower and measurements. | See below Tab: "Org Chart" | Done | Elisa | [8 empty] | Morning
Big Case Estimation, Budget & ROI | 10% error margin. The project's perimeter is not specifiable to 100%. | S360-SAF-ROI-23Q3-TEAM-V0.1.xlsx |  | Etienne | [8 empty] | Morning | [20 empty] | KICK OFF! | [37 empty] | GO LIVE!
Organization chart | Organigram creation to fluidify the organization of work. | See below Tab: "Organigrams" | Done | Dyhia | [8 empty] | Morning | [20 empty] | KICK OFF! | [37 empty] | GO LIVE!
Risk Matrix | We need to explain this to the client who has no clue. This is something that we elaborate with the customer after having drawn a risk matrice. This is the most accurate (precise) document available on the finished project. | S360-SAF-RISK_MATRIX-23Q3-TEAM-V0.1.xlsx | Creation by Atif and Elisa. Almost done. Needs translation and reevaluation of criticality factorization. | Atif | [12 empty] | Morning | Morning |  | Evening | Morning | [12 empty] | KICK OFF! | [37 empty] | GO LIVE!
Comitees organization | Create a planning foretelling every comitee during the project, with explanation of the results of each meeting to follow the project and the relations between stakeholders. | See below Tab: "Comitology" | To be actualized in Real-Time | Samira | [8 empty] | Morning | [20 empty] | KICK OFF!
Documentary Naming Convention | Consists of four parts separated by an underscore to identify the document. | S360-SAF-NAMING_CONVENTION_SALESFORCE_CRM_ALPHA-23Q3-OPEN.V1.pptx | Codification and proofreading procedure to be edited | Elisa | [12 empty] | Morning | [16 empty] | KICK OFF! | [37 empty] | GO LIVE!
List of deliverables | List of every deliverable with agreements on how to evaluate the ongoing of each one: done/not done, percentage, number of versions. It allows visibility upon the advancement of the project. | S360-SAF-LIST OF DELIVERABLES-23Q3-REST-V.01.pptx | Must decide if the completion of material tasks (software implementation and integration) should be added to the list of deliverables, or if it is only about documentation. | Fanta | [13 empty] | Morning | [15 empty] | KICK OFF! | [37 empty] | GO LIVE!
Marketing KPIs Workshop | With the Client in order to define the KPI Marketing | S360-SAF-REQUIREMENTS REVIEW-23Q3-OPEN-V1.docx | Done | Collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Marketing KPI definition | Define which elements can be taken into account to assess the project's evolution: Progress in % ; Gap between expected deadline VS reality​ ; Finances: Expected budget VS Actual consumption. | S360-SAF-REQUIREMENTS REVIEW-23Q3-OPEN-V1.docx | Included in the Requirements reviews | Collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Workshop with Elizabeth, Sales & Mark. Director | Planning a workshop to evaluate the cost of product selling in terms of hours worked by salespersons | Data included in ROI | Done | Etienne
ROI calculation | Calculating the ROI. To be presented next Steering Comitee. | S360-SAF-ROI-23Q3-TEAM-V0.1.xlsx | Waiting improvement with Elizabeth's workshop on time economy of sale making. | Etienne, collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Feasibility study | Risk analysis to define acceptable margins of error. | S360-SAF-FEASIBILITY STUDY-23Q3-OPEN-V1-23Q3-TEAM-V0.1.xlsx | Done | Elisa, Dyhia | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
S360-SAF-FEASABILITY STUDY-23Q3-TEAM-V0.2 - Copy.docx
Commercial proposition | Indicative as we are working internally within the company. Not mandatory as pricing is already included in Budget and ROI. | Not mandatory | Not mandatory | Not mandatory | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Deliverables validation | Must plan to create a column in the list of deliverable to link final and validated version of deliverables (PDF). | S360-SAF-LIST OF DELIVERABLES-23Q3-REST-V.01.pptx | Waiting for validation of the Direction. | Samira
Blueprint | Everything the client needs, wants, and is realisable. (But this is not "how" we're gonna do it.) Max of information/min of ressources. | S360-SAF-BLUEPRINT-23Q4-OPEN-V0.4 | Waiting for validation. | Dyhia | [13 empty] | Morning | [15 empty] | KICK OFF! | [37 empty] | GO LIVE!
Go,No go | [33 empty] | KICK OFF!
DESIGN PHASE | [33 empty] | KICK OFF! | [37 empty] | GO LIVE!
Hardware Resources Definition | Materials needed: 8 computers + 8 mouses + Internet connection (Account 78112. "Immobilisations corporelles") [Amortization] The Cloud SI infrastructure is taken in charge by Salesforce. | See the case on the left | Done | Collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Software Resources Definition | Salesforce licences and editions. to be included in the budget. | See below Tab: "Budget" | In progress. To be included in the ROI calculation. | Collaborative | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Ekovya Website Sandbox | Developer/Sandbox edition of the website to not work directly into production. | https://sandbox.ekovya.com/wp-admin/ | Menu Elementor not working. User : smm@ekovya.com Pass : ??? | Amos
Ekovya Website Design | Creation of website design: structure and content without e-commerce. | https://www.figma.com/file/wxyXPHc0l859PU6PCVzcbz/Website-Mock-up?type=design&mode=design&t=ryG0hWZ5bFuAmwUq-1 | Elisa: “Blog Ekovya”, Menu and footer. Samira: “Qui sommes-nous ?” Mohamed: “Contact” Fanta: “Infos pratiques” Dyhia et Olivier: “Accueil”, “Rejoignez-nous” | Collaborative
E-Commerce Design | Anticipating how the catalogue will be presented on the e-commerce website. The e-commerce will be accessible on the one and only website, via the menu directing to the page "Catalogue". Creation of a model (visual only). ISSUE: No native "request quote" button in WooCommerce => Search for plug-in. | https://www.figma.com/file/wxyXPHc0l859PU6PCVzcbz/Website-Mock-up?type=design&mode=design&t=pdNpACuQVF9QvZKM-1 | graphic_chart_ekovya.pdf | Collaborative
Website Mock-Up Design | Creation of a visual representation of the website. | In Progress | https://www.figma.com/file/wxyXPHc0l859PU6PCVzcbz/Website-Mock-up?type=design&node-id=0%3A1&mode=design&t=zfdwDG2P2957aj27-1 | Etienne, Fanta
Product Sheets Mock-Up Design | Creation of a visual representation of product layouts on e-commerce website. | EKOVYA_SIGMA_360_PRODUCT_SHEET_MOCK-UP V1.1.png | https://www.figma.com/file/6gjjE67dBt8p3T5p69Z8pO/EKOVYA_SIGMA_360_PRODUCT_SHEET_MOCK-UP?type=design&node-id=0%3A1&mode=design&t=2cB8L1DZFNdGQfs3-1 | Etienne
Information System Architecture | Providing visual representation of the information eco-system, describing how each software is used and connected. Must provide insights on project's scope. (What is meant to be deployed and integrated within time limit). | EKOVYA_SIGMA360_SAF_SI_ARCHITECTURE_23Q4_V0.4.jpg | https://www.figma.com/file/Bl364P4GQqynwWhOpna9Hi/Untitled?type=design&node-id=0%3A1&mode=design&t=GHIlsmAr5Ek8ygYW-1 | Etienne
BP Customer Journey Design | The main Business Process, modeling the customer journey and the associated data in the data architecture. | Ekovya's customer jour... ¦ EKOVYA | Fidelisation phase to be written. | Dyhia | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
BP "Lead to Opportunity" Design | Designing how customer e-mails are going to be recuperated and transferred in Salesforce, then used for mail deliverance and campaigns (Brevo?). | Ekovya's BP Lead To Op... ¦ EKOVYA |  | Mohamed, Samira
BP "Opportunity to Customer" Process Design | Designing how the payment via the website will be processed and sent to both Salesforce and SAP to command the expedition of products. | Editing Page Ekovya BP Opportunity ... ¦ EKOVYA | BP SAP Rétroplanning Organisation-Activity-Phase ERP 7 V 0.5,.xlsm | Etienne, Yoann, Mohamed
BP "Mailing Campaign" | Designing how mails will be distributed, why, when, and via which chanel. | Ekovya BP Mailing Camp... ¦ EKOVYA |  | Olivier
BP "Sales to Service" | Customer Reclamation BP Design | Ekovya BP Sales to Ser... ¦ EKOVYA | Waiting for validation by Elizabeth | Dyhia, Fanta, Atif
KPIs Recuperation Process | Which KPI can be captured, when and by which BP. See case on the right => | Exception made of the "Cart Abandon Rate", which is included in the BP Customer Journey because it involves an automatic marketing action (=> an e-mail reminder), all KPIs will be collected via Google Analytics and Google Ads, or will be available directly in WooCommerce or in Salesforce's Reports & Dashboards. | The "Cart Abandon Rate" is Included in the BP Mailing because it is used as an Marketing Automation Input | Olivier, Dyhia, Etienne
Hubspot data migration design | Canceled | Canceled by decision of Alexandre | Waiting for Hubspot Access | Canceled
MCD creation | Creation of the Data Conceptual Model. | https://edumotic.sharepoint.com/:b:/s/EKOVYA/EX4xPxQqF5REioRlz-rh_N8B0ACN83aWn6VEbdd4AvPbIQ?e=TBCOBg | Accessible on Salesforce | Atif, Dyhia, Etienne, Mohamed | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Authorizations matrix | Sales Representatives: permission to access their own records, sales functions, parts of reporting, and the ability to show the level of stock. | S360-SAF-AUTHORIZATIONS_MATRIX-23Q4-OPEN-V0.1 |  | Etienne, Dyhia | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
BUILD PHASE | [33 empty] | KICK OFF! | [37 empty] | GO LIVE!
Salesforce Sales Cloud Professional Edition License Purchase |  |  | Ask Alexandre to buy Sales Cloud licenses*2 | Etienne
Connecting Google Analytics to Wordpress |  | Done |  | Fanta, Dyhia, Etienne
Develop products catalogue | Creation and update of the products catalogue. | CATALOGUE EKOVYA 2023.pptx |  | Elisa, Olivier | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Mapping product Salesforce to Woocommerce | Match fields in both system |  | Etienne et Atif : Product ; Samira et Mohamed : Customer ; Order : Fanta Dyhia | Equipe
Caterory pages creation |  |  | Olivier | Olivier
Connecting Salesforce to WooCommerce with PowerAutomate |  |  |  | groupe 1: Mohamed, Samira, Groupe 2: Fanta, Dyhia
Create automated flows between WooCommerce and Salesforce |  |  | Etienne : Product ; Samira, Olivier et Mohamed : Customer ; Order : Fanta Dyhia et Elisa en support
Connecting Brevo to Salesforce | DOMO ? |  |  | Fanta
Event bus programmation | Organizing chronologically automation of API request between systems | Important | Using Mulesoft | Mohamed
Monitoring data transfer | Providing monitoring tools to manage API data flows between systems. | Important | Using Mulesoft | Mohamed
Connecting Google Analytics to Salesforce |  |  |  | Dyhia, Etienne
Connecting SAP to Salesforce | Establishing scheme to transfer data from SAP to Salesforce. Need regular official meetings with SAP team. Using Mulesoft/Power Automate/Talend as a middleware. Working in cooperation with a person of the SAP team (Yoann). Must collect all required data field from SAP. (See mail from Yoann) | SAP-SALESFORCE Connexion | BP SAP Rétroplanning Organisation-Activity-Phase ERP 7 V 0.5,.xlsm | Mohamed, Fanta, Etienne
PRE-PRODUCTION | Making sure that the development editions are ready to switch into Production edition. | Coming soon | [31 empty] | KICK OFF! | [37 empty] | GO LIVE!
Website Pre-Production | Preparing DEV in anticipation of PROD transfer. | S360-SAF-LIST_API_KEYS_EKOVYA_COM-OPEN-23Q4-V0.1 | Must add products, e-commerce design, account creation form and registration to newsletter. | [30 empty] | KICK OFF! | [37 empty] | GO LIVE!
Brevo Pre-Production | Preparing DEV in anticipation of PROD transfer.
Google Analytics Pre-Production | Preparing DEV in anticipation of PROD transfer. |  |  | Dyhia
Publer Pre-Production | Preparing DEV in anticipation of PROD transfer.
Salesforce Pre-Production | Preparing DEV in anticipation of PROD transfer.
SAF <=> SAP Pre-Production | Preparing DEV in anticipation of PROD transfer. | [32 empty] | KICK OFF! | [37 empty] | GO LIVE!
DELIVERY PHASE | [33 empty] | KICK OFF! | [37 empty] | GO LIVE!
CUSTOMIZING GUIDES WOOCOMMERCE |  | S360-SAF-CUSTOMIZING GUIDE WOOCOMMERCE-23Q4-TEAMS-V0.1 |  | Elisa, Olivier
CUSTOMIZING GUIDES WEBSITE |  | S360-SAF-CUSTOMIZING GUIDE WEBSITE-23Q4-TEAMS-V0.1 |  | Fanta et Etienne
CUSTOMIZING GUIDES SALESFORCE | One guide for each Business Process (or each user profile). | S360-SAF-CUSTOMIZING GUIDE SALESFORCE-23Q4-TEAMS-V0.1 |  | Atif, Dyhia, Samira
TRAINING GUIDES | To be build from the End Users Guide and optimized for training. (No concrete training phase in this project). | S360-SAF-SALESFORCE USER TRAINING-23Q4-OPEN-V0.1.pptx |  | Atif, Dyhia, Samira | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
END USERS GUIDES / SALESFORCE | One guide for each Business Process (or each user profile). | Documentation expected |  | Atif, Dyhia, Samira | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
TRAINING GUIDE UAT | Learning support to teach users how to use Squash for tests campaigns | Squash TM ¦ EKOVYA |  | Yoann
TESTS LIST | List test according to each dates of evaluation. | S360-SAF-LIST UAT-23Q4-TEAMS-V0.1 |  | Samira, Dyhia, Etienne, Elisa
UAT | 10/11/2023 (Started 08/11) Need to be over 90% success rate with no critical blocking. 1 day duration. Must use Squash to procedure formalization. | 13_UAT | 08/11/2023 - First step: training - complete Participants: Marjorie, Sophia, Assia 10/11/2023 - Second step - complete Participants: , Sophia, Assia | Elisa, Etienne, Olivier, Samira | [29 empty] | KICK OFF! | [37 empty] | GO LIVE!
Corrective reparation | [33 empty] | KICK OFF! | [37 empty] | GO LIVE!
Payment | If UAT = OK => payment | [32 empty] | KICK OFF! | [37 empty] | GO LIVE!
PRODUCTION
Website Production | Implementing DEV settings into PROD environment.
Brevo Production | Implementing DEV settings into PROD environment. |  |  | Dyhia
Google Analytics Production | Implementing DEV settings into PROD environment.
Publer Production | Implementing DEV settings into PROD environment.
Salesforce Production | Implementing DEV settings into PROD environment.
SAF <=> SAP Production | Implementing DEV settings into PROD environment.
GO LIVES (Milestones, not events, neither tasks)
Website Go Live
Brevo Go Live |  |  |  | Dyhia
Google Analytics Go Live
Publer Go Live
Salesforce Go Live
SAP + SAF Go Live
GLOBAL GO LIVE! |  | 2023-11-22 | [31 empty] | KICK OFF! | [37 empty] | GO LIVE!
Post-work Plan | A detailed plan that resume the original design updated with the concrete realizations of the project. | [32 empty] | KICK OFF! | [37 empty] | GO LIVE!
Critics Neutralization | Be aware of resistance among the organization and delegate at least two people at the same time to coach people who complains about the software solution. | [32 empty] | KICK OFF! | [37 empty] | GO LIVE!
RSV - Regular Verification in Service | Being available to answer customer's questions before charging for maintenance.

## UAT & Go Live
| November | [9 empty] | December
| 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Morning | Elisa, Olivier, Atif, Etienne: Steering Committee (done) | Etienne: set up Front-end tests Elisa: set up Back-end tests Olivier: set up Publer tests Fanta: Go Live website -> collect pictures with Lotfi + proposal to Alexandre. Atif: Training+End-User guides -> based on successfull UAT instructions | Samira: declare issues on OpenProject Dyhia: set up Salesforce unit tests Mohamed: Technical documentation -> update the list of fields used for integration Olivier: set up Brevo tests | Elisa, Etienne, Olivier, Dyhia: Units UAT* & training Samira: set up Flow: Create Customer Account Fanta: create Price Book in SAF | WEEK-END | WEEK-END | Dyhia: integrate Brevo to Woocommerce + DOCUMENTATION Olivier: integrate Brevo to Salesforce + DOCUMENTATION Etienne: set up flow: Delete products Samira: set up flow: Update Customer Account/Contact | All: fill hours in Open Project Etienne: set up flow: Stock-level of products from SAF to WOO Dyhia, Olivier: Integrate Publer to SAF + DOCUMENTATION Mohamed: CUSTOMIZING GUIDE | SQUASH TEST SETTING | Patrick Delannoy | Patrick Delannoy | WEEK-END | WEEK-END | UAT INTEGRATION | DEV: Connexion Google Analytics to SAF DEV: Connexion SAP to SAF
Afternoon | Elisa, Etienne: Planification (done) | Etienne: set up Flow: Create products | Etienne: Go Live Salesforce -> proposal to Alexandre (?new DEV edition?) Mohamed: Continue technical documentation of integrated fields Dyhia: set up flow: Create Order + Mail Notification (to Sales Reps) | Etienne: set up flow: Update products Olivier: set up flow: Customer Account -> Mail Notification (x3) Mohamed: Create a document gathering all accesses of DEV editions accounts (starting CUSTOMIZING GUIDE) | WEEK-END | WEEK-END | Samira: set up flow: Delete Customer Account/Contact Etienne: set up flow: Products -> Mail Notification Olivier: preparation Go Live Brevo | Mailing Automation to customer: 1. Newsletter subscription confirmation 2. Contact message confirmation 3. Account creation confirmation 4. Order confirmation | LAST MINUTE ADJUSTMENTS | Patrick Delannoy | Go Live: Website Go Live: Salesforce Go Live: Brevo Go Live: Publer | WEEK-END | WEEK-END | 15h30: Axe Committee
Notes |  | Olivier: Creates Mail notification when Account creation in WooCommerce: send mail to customer and Sales Rep. Etienne: Convention naming PwrAut flows. /!\ Issue: Salesforce does not collect all Lead data. /!\ Issue: How to use "Get Record" to send a confirmation email after collecting Lead data on website form? Elisa: Coordination Documentary | Olivier : Creation test pour Brevo. Difficultées pour Pubbler car l'utilisation de l'adresse mail similaire à Brevo ne fonctionne pas. --> Pas de test pour Pubbler Elisa : Point sur la gestion documentaire avec Yoann + mail equipe | Training Etienne: Test BREVO et FRONT END fait avec Sophia Elisa : bloquée sur test back end suivants : gestion des prix par rapport catégorie clien; affichage panier moyen et affichage taux abandon panier mais ok pour prix degressif en fonction qté ; affichage nombre de commande par client ; affiche numero commande par client |  |  |  | 3. Account creation confirmation => (ok) | Etienne: Products Flows: 1. Create Woo product -> Saf product + Price Book Entry (ok) 2. Update Woo product -> Saf product + Price Book Entry (ok) 3. Delete Woo product -> Saf product + Price Book Entry (ok) Samira: Customer Flows: 1. Create (ok) 2. Update (ok) 3. Delete (ok) Samira, Fanta, Mohamed: Order Flows: 1. Create (ok) Olivier: validation training guide Salesforce Olivier et Dyhia: Customizing guide BREVO Samira et Fanta : Point avec Yohann gestion docs. désicion suite au point : Transférer la nouvelle convention de nommage à l’équipe . Elisa : mail de relance pour comité de décision et bilan de projet. Partage des tâches (KANBAN), point avec les differentes personnes |  | Etienne et Elisa : préparation comité de décision Elisa : Mail pour rappel saisie heures Elisa : mail Elisabeth pour info planif UAT Elisa : planification cours Amos gestion mots de passe Elisa : réponse Elisabeth qui sera là aux UAT et comité decision |  |  | Etienne et Elisa : UAT avec Sophia et Elisabeth Axe comitee : mise en production non accepté. il faut faire les modifs pour une prise de decision mercredi 6 | TEAM : reunion bilan projet Elisa: point autonomie sur ptn abordés en axe comitee. modif powerpoint (3 colonnes UAT)
*Units UAT : testing each software independently
Note on C3: Etienne BERNOULI [EKVY]:

## Time Tracking
SIGMA 360 PROJECT - Working time tracking
| Etienne |  | Samira |  | Mohamed |  | Elisa |  | Atif |  | Fanta |  | Olivier |  | Dyhia
Date | Task | Hours | Task | Hours | Task | Hours | Task | Hours | Task | Hours | Task | Hours | Task | Hours | Task | Hours
Monday 21 August
Tuesday 22 August
Wednesday 23 August
Thursday 24 August
Friday 25 August
Monday 28 August | Project Planification | 3 | Project Planification | 3 | Project Planification | 3 | Project Planification | 3 | Project Planification | 3 | Project Planification | 3 | Project Planification | 3 | Project Planification | 3
Tuesday 29 August
Thursday 31 August | Reception of needs | 2 | Project Planification | 3 | Reception of needs | 2 | Ishikawa's diagram | 3 | Ishikawa's diagram | 3 | Abs | 0 | Reception of needs | 2 | Reception of needs | 1
| Requirements review | 1 | Comitology | 1 | Requirements review | 2 | [6 empty] | Requirements review | 2 | Organisation chart | 1
Friday 1 September | Restricted Comitee | 4 | Restricted Comitee | 4 |  | ABS | Restricted Comitee | 4 | Restricted Comitee | 4 | Restricted Comitee | 4 | Restricted Comitee | 4 | Restricted Comitee | 4
Wednesday 6 September | Landscape definition | 1 | Macro-planning design | 2 | Landscape definition | 2 | Ishikawa's diagram | 3 | Landscape definition | 1.5 | List of deliverables | 3 | Requirements review | 1.5 | Macro-planning design | 1.5
| Naming convention | 2 | Naming convention | 2 | Naming convention | 2 | Naming Convention | 2 | Naming Convention | 2 | Naming Convention | 2 | Naming Convention | 2 | Naming Convention | 2
| Big Case Estimation (Budget) | 1 | [6 empty] | Ishikawa's diagram | 2 |  |  |  |  | Blueprint | 1
Thursday 7 September | Risk Matrix | 3 | List of deliverables | 0.5 | Salesforce technique | 4 | Risk Matrix | 3 | Risk Matrix | 3 | List of deliverables | 3 | Requirements review | 3 | Blueprint | 3
|  |  | Blueprint | 0.5
Friday 8 September | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4 | Scoping workshop | 4
Monday 11 September | Planification: Gantt Diagram/Open Project | 3 | Web design | 3 | Web design | 3 | Risk Matrix | 1 | Risk Matrix | 3 | List of deliverables | 3 | Web design | 3 | Web design | 3
| Requirements review | 1
Tuesday 12 September | Risk Matrix | 1 | Web design | 2 | Web design | 2 | Risk Matrix | 3 | Risk Matrix | 2 | List of deliverables | 2 | Web design | 2 | Web design | 2
| Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2 | Restricted Comitee | 2
| Planification: Time tracking | 1 | Web design | 3 | Web design | 1.5 |  |  | Risk Matrix | 3 | List of deliverables | 3 | Web design | 3 | Web design | 3
Wednesday 13 September | Planification: Costs Control | 0.5 | Web design | 7 | Web design | 7 | WebSite | 3 | Web Design | 7 | Web Design | 3 | Web design | 7 | Web design | 7
Thursday 14 September |  |  | Web design | 7 | Web design | 7 |  |  |  |  | Web Design | 7 | Web design | 7 | Web design | 7
Friday 15 September | Team meeting | 1 | Team meeting | 1 | Team meeting | 1 | Team meeting | 1 | Team meeting | 1 | Team meeting | 1 | Team meeting | 1 | Team meeting | 1
| Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1 | Risk Matrix | 1
| ROI | 1 | ROI | 1 | ROI | 1 | ROI | 4.5 | ROI | 1 | ROI | 1 | ROI | 1 | ROI | 1
[15 empty] | Blueprint | 1
Monday 18 September | ROI page layout | 2 | Steering Committee organization | 2 | ROI | 2 | ROI estimation | 3 |  |  |  |  | ROI translation | 1
| Requirements review page layout | 2 | Web design | 5 | Web design | 5 | Web design | 4 |  |  | Web Design | 7 | Web design | 6 | Web design | 7
Tuesday 19 September | Webdesign | 2 | Web design | 3 | Web design | 5 | Web design | 5 | Web design | 7 | Web design | 7 | Web design | 7 | Web design | 5
| ROI | 3 | Steering Committee organization | 2 |  |  | Proofeading "review requirements" | 1.5 |  |  | Proofeading "review requirements" | 1.5 |  |  | Blueprint | 1
| Steering Committee preparation | 1
Wednesday 20 Sept | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3 | Restricted Comitee | 3
| Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3 | Requirements review page layout | 3
| Organisation | 1 | Organisation | 1 |  |  |  |  | Organisation | 1
Thursday 21 Sept | Planning | 3.5 |  |  |  |  | Feasibility study | 5 | Risk Matrix | 7 | Feasibility study | 7 | BP definition | 5.5
| Feasibility study | 1
| BP Definition | 1
| Risk Matrix | 1.5 | [12 empty] | Feasability study | 3
| Planification | 1 | [12 empty] | Blueprint | 4
Friday 22 Sept | Planification | 3.5 | Planning | 3.5 |  |  |  |  | BP Definition | 3,5 | Feasibility study | 7
| Planification | 3.5 | Macro-planning | 3.5
Tuesday 26 Sept | ROI | 0,5 | [12 empty] | Blueprint | 1
Wednesday 27 Sept | Coordination | 6,5
| Planification | 0,5
Thursday 28 Sept | Coordination | 7
Friday 29 Sept | Team meeting | 3.5
| Planification | 3.5
Wednesday 4 Oct | Planification | 3.5
| Product Maquette | 3.5
Tuesday 5 Oct | Planification | 3.5
| Product Maquette | 3.5
Friday 6 Oct | Blueprint | 3.5
| Blueprint | 3.5
Monday 9 Oct | Website Design | 1
| Planification | 2
| Blueprint | 4
Tuesday 10 Oct | Website Mock-Up | 5
Wednesday 11 Oct | BP Design | 3.5
| Planification | 2
Thursday 12 Oct | Website Mock-Up | 3.5
Friday 13 Oct | BP Design Connexion SAP SAF | 3.5
| BP Design Connexion SAP SAF | 3.5
Monday 16 Oct | Website Design | 3.5
| MCD | 3.5
Tuesday 17 Oct | BP design | 3.5
| SI mapping | 3.5
Thursday 19 Oct | BP Definition | 3.5
| Planification: Pl. & Costs Control | 3.5
Friday 20 Oct | Copil | 3.5
Tuesday 24 Oct | IS Architecture | 3.5
Wednesday 25 Oct | Web design | 7
Monday 30 Oct | Webdesign | 3.5
| Salesforce Setting | 3.5
Tuesday 31 Oct | Salesforce Setting | 3.5
Thursday 02 Nov | Website design | 7
Friday 03 Nov | Website Design | 7
Sunday 05 Nov | Planification | 3
Monday 06 Nov | Pre-Steering Committee | 3.5
Tuesday 07 Nov | Planification | 3.5
| UAT | 3.5
Wednesday 08 Nov | UAT | 7
Thursday 09 Nov | UAT | 3.5
Friday 10 Nov | UAT | 7
Monday 13 Nov | MCD | 3.5
Tuesday 14 Nov | Integration | 7
Wednesday 15 Nov | Integration | 7
Thursday 16 Nov | Integration | 3.5
| Planification | 3.5
Tuesday 21 Nov | Steering Committee | 3.5
| Planification | 3.5
Thirsday 23 Nov | Integration | 3.5
| Planification | 3.5
Tuesday 28 Nov | Integration | 7
Wednseday 29 Nov | Integration | 7
Monday 04 Dec | UAT | 3.5
| Axe Committee | 3.5
Tuesday 05 Dec | Documentation Project Completion Review | 7
Wednesday 06 Dec | Documentation Project Completion Review | 7
Thursay 07 Dec | Documentation UAT | 7
Total worked hours |  | 298.5 |  | 73 |  | 62.5 |  | 62 |  | 63.5 |  | 77.5 |  | 74 |  | 75.5 | 786.5
[17 empty] | Total Cost | 53953.9
[17 empty] | Hourly patronal cost of a consultant | 68.6
3

## Duration of activities
¦ week ¦ Activity ¦ Estimated Duration ¦
¦---------¦---------------------------------------------------------¦---------------¦
¦ 1 ¦Reception of needs / workshop ¦ 1-2 weeks ¦
¦ 1 ¦ Landscape presentation ¦ 1 week ¦
¦ 2 ¦ Scoping ¦ 2 weeks ¦
¦ 3 ¦ Requirements review ¦ 2-3 weeks ¦
¦ 4 ¦ Risk Analysis/Assessment ¦ 1 week ¦
¦ 4 ¦ Cahier des charges/Blueprint ¦ 3-4 weeks ¦
¦ 5 ¦ Business Processes Definition ¦ 2-3 weeks ¦
¦ 5 ¦ Big Case Study ¦ 1 week ¦
¦ 6 ¦ feasability study => Go, No go ¦ 1 week ¦
¦ 6 ¦ Commercial proposition ¦ 2 weeks ¦
¦ 7 ¦ List of deliverables creation ¦ 1 week ¦
¦ 7 ¦ Organization chart ¦ 1 week ¦
¦ 8 ¦ MCD creation ¦ 2 weeks ¦
¦ 8 ¦ Business Processes Design ¦ 3-4 weeks ¦
¦ 9 ¦ Authorizations matrix ¦ 1-2 weeks ¦
¦ 10 ¦ Documentary Naming Convention ¦ 1 week ¦
¦ 10 ¦ Schedule management ¦ In progress ¦
¦ 11 ¦ Sales funnel creation ¦ 2-3 weeks ¦
¦ 12 ¦ List product catalogue ¦ 2 weeks ¦
¦ 12 ¦ Website creation ¦ 4-6 weeks ¦
¦ 13 ¦ Data migration Hubspot ¦ 3-4 weeks ¦
¦ 13 ¦ Implementation SAF => SAP ¦ 4-6 weeks ¦
¦ 14 ¦ Prototyping ¦ 2-3 weeks ¦
¦ 14 ¦ Unit Testing ¦ In Progress¦
¦ 14 ¦ Performance Testing ¦ 2-3 weeks ¦
¦ 14 ¦ Usability Testing ¦ 1-2 weeks ¦
¦ 14 ¦ Integration Testing ¦ In progress ¦
¦ 14 ¦ END USERS GUIDE ¦ 2-3 weeks ¦
¦ 14 ¦ UAT ¦ Variable ¦
¦ 14 ¦ Payment ¦ Variable ¦
¦ 14 ¦ GO LIVE! ¦ 1 day ¦
¦ 14 ¦ Training guide ¦ 2 weeks ¦
¦ 14 ¦ Training ¦ 2-3 weeks ¦
¦ 14 ¦ Critics Neutralization ¦ In progess ¦
Regular verification in service

## Org Chart
Organigram ALPHA CRM
ORGANIGRAM CRM 1 V1.pptx
| Roles |  | Managers
| GED | "Gestion Electronique des Documents" | Fanta, Samira
| PM/PMO | "Project Manager (Officer)" | Etienne, Samira, Elisa | (11 sept, 11 oct, 11 nov)
| IQ | "Ingénieur.e Qualité" | Atif
| IT | "Ingénieur.e Technique" | Mohamed MOHAMO, Olivier
| PCC | "Planner & Cost Controller" | Etienne
| CM | "Contract Manager" | Elisa, Dyhia
| DC | "Directrice Commerciale" | Elizabeth
Major tasks
Website creation - ecommerce (creation of product pages)
Website connexion to the CRM Salesforce
Data migration from Hubspot et Dolibarr to Salesforce
Integration between Salesforce and SAP
Marketing Automation (Newsletter)
| 1 | President | José Gaultier
| 2 | Vice President Chief Financial Officer | Alexandre Gain Gilles Sauvageon
| 3 | Direction (5?) | Philippe Bassot (Program Manager and Director Ekovya Consulting)
Elizabeth Golovanov (Sales and Marketing and Director Ekovya Solutions)
Lotfi Rebiai (Expert Marketing Digital and Business Intelligence)
Alain Claude (Expert Salesforce)
Nancy Guenat (Responsable Communication)
Pierre Dauvergne (Externe Communication Consultant)
For SAP: Lionel Rinaldi (External Consultant Spec. Project Management)
Ishikawa's diagram
https://wiki.ekovya.com/books/sigma360-salesforce-crm1-2023/page/diagramme-ishikawa

## Comitology
Steering Comitees CRM Alpha 2023
Month | Date | Presentation | Number of Consultants | Who? | Convocations | Agenda (Order of the day) | ANNULER
September - Pre Steering Committee | 2023-09-12 | Project discussion | 8 | Everyone | X | Requirements review and presentation of deliveries' creation progress.
September | 21/09/2023 !new date! -20/09/2023- | Presentation By Etienne, Fanta, Atif | 8 | Everyone | To be sent | List of deliverables, ROI, Requirements Review, Risk Matrix (ask about factorization of criticity)
September Director Board | 27/09/2023 | Etienne | ? | Alexandre and a team of new people just arriving. | ? | Discussing HR costs to refine budget calculation.
October - Pre-Steering Committee | 2023-10-11 | Etienne | ? | With Gilles and Alexandre. 1h30. Starting at 9h15 | To be sent | 1. PARCOURS CLIENT 2. MAQUETTE SITE 3. MAQUETTE PRODUIT 4.VERIFIER LES HEURES&TICKETS SUR OPEN PROJECT
October Steering Committee | 2023-10-20 | Samira | 8 | Everyone | To be sent | ARCHITECTURE Mapping BP INTEGRATION SAP-SAF (VISUAL) - CURRENCY COORDINATION WITH SAP (CHANGE RATE) Websites must be ready to go online
October Director Board | 2023-10-25 | Samira
PRE-COPIL | 2023-11-06 | Samira, Elisa, Etienne | PMOs
UAT start | 2023-11-10 |  |  |  |  | Intermediate UAT
Steering Comitee | 2023-11-21 |  | 8 | Everyone | 9h30 | Unit Test terminated Salesforce part Ready
Director Board | 2023-11-22 |  |  |  | ?9h30? | Postpone
GO LIVE | 2023-11-22
December
Axe commitee | 2023-04-12 | Production ? | 8 | Team | In progress | Postpone 06/12/2023
Axe commitee | 2023-06-12