## Slide 1: List of deliverables
Responsible of Document: Fanta GABY
Author: Fanta GABY, 06/09/2023 Validation:
Last update:
Proofread: Samira MHAMSA, 28/09/2023

## Slide 2: Progress agreement convention
Progress in % | Description | Responsible for validation
0% | Not started yet or insignificant progress | Consultant itself
25% | In progress | Consultant itself
50% | Advanced progress | Task referent
75% | 1st validation proposal | Project Manager Officer
100% | Final validation | Project director

## Slide 3: Deliverables snapshot (1/3)
Deliverables | Who | Status | Version | Comments
Requirements review | Olivier Chanthaseng | 100% | V.1 | Second validation Progress
Scoping Note | Elisa Fauci | 75% | V0.1 | First validation Progress
Big case estimation / ROI | Etienne Bernouli | 75% | V0.1 | First validation Progress
Macro Planning | Samira Mhamsa | 75% | V0.1 | First validation Progress
Feasibility Study | Elisa Fauci/Dyhia Amour | 75% | V0.1 | First validation Progress
Org Chart | Dyhia Amour | 75% | V1 | Validated
Blueprint | Dyhia Amour | 75% | V0.1 | First validation progress

## Slide 4: Deliverables snapshot (2/3)
Deliverables | Who | Status | Version | Comment
Product Sheets Mock-Up | Etienne Bernouli | 75% | V0.1 | First validation Progress
Architecture Mapping | Samira Mhamsa | 75% | V0.1 | In progress
Website Mock-up | Fanta Gaby | 75% | V0.1 | First validation progress
Business Process Quote To cash (SAP) |  | 0% | V0.1 | Not started yet
Business Process Customer Journey | Dyhia Amour | 0 % |  | Not started yet
Business Process Order To cash |  | 0% |  | Not started yet

## Slide 5: Deliverables snapshot (3/3)
 | Who | Status | Version | Comment
Migration kit |  | 0% | V0.1 | Not started yet
Authorizations matrix |  | 0% | V0.1 | Not started yet
Customizing and tests reports |  | 0% | V0.1 | Not started yet
Customizing guide Salesforce |  | 0% | V0.1 | Not started yet
Business Process Website/E-commerce |  | 0% | V0.1 | Not started yet
End users guide |  | 0% | V0.1 | Not started yet
Business Process Salesforce integration |  | 0% | V0.1 | Not started yet
Business process documentation |  | 0% | V0.1 | Not started yet

## Slide 6: RASCI
ID | Responsible | Accountable | Support | Consulted | Informed
Requirements review | Olivier Chantaseng |  | Mohamed Mhamo | Etienne Bernouli | 
Risk analysis/ Assessement | Atif Satif |  | Elisa Fauci |  | 
Big Case estimation | Etienne Bernouli |  |  |  | 
ROI | Collaborative |  |  |  | 
Blueprint | Dyhia Amour |  |  |  | 
Org Chart | Dyhia Amour |  | Samira Mhamsa |  | 
Feasibility study | Elisa Fauci |  | Dyhia Amour | Fanta Gaby | 
Products Sheets Mock-Up | Etienne Bernouli |  | Fanta Gaby |  | 

## Slide 7: RASCI
ID | Responsible | Accountable | Support | Consulted | Informed
Architecture Mapping | Samira Mhamsa |  |  |  | 
Website Mock Up |  |  |  |  | 
Business Process Customer Journey | Dyhia Amour |  |  |  | 
Business Process Q2C (SAP) |  |  |  |  | 
Business Process O2C |  |  |  |  | 
Customizing Guide Salesforce |  |  |  |  | 
End User Guide |  |  |  |  |