## Sheet1
SIGMA 360 PROJECT
List of deliverables CRM Alpha
Responsible of Document: Fanta GABY
Author: Fanta GABY 27/09/2023
Validation:
Last update:
Proofread: Samira MHAMSA 27/09/2023
| Who | Status | Version | Comments
Requirements review | Olivier Chantaseng | 80% | V1.0 | In Progress
Risk analysis / Assessement | Atif Satif | 80% | V0.1 | In Progress
Big Case estimation | Etienne Bernouli | 80% | V0.1 | In Progress
ROI | Collaborative | 50% | V0.1 | In Progress
Blueprint | Dyhia amour | 70% | V0.1 | In Progress
Org Chart | Dyhia Amour | 80% | V0.1 | In Progress
Feasibility study | Elisa | 70% | V0.1 | In Progress
Authorization matrix |  | 0% |  | Not started yet
Business Process KPI |  | 0%
Business Process Website |  | 0% |  | Not started yet
Business Process Order To Cash |  | 0% |  | Not started yet
Business Process Quote To Cash |  | 0% |  | Not started yet
Migration Kit |  | 0% |  | Not started yet
Design Website |  | 0% |  | Not started yet
Customizing guide |  | 0% |  | Not started yet
End User Guide |  | 0% |  | Not started yet
Business Process Documentation |  | 0% |  | Not started yet
Légende
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quelle est la définition de chaque livrable ?
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Que veulent dire les pourcentages ? Y a-t-il une légende ?
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pourquoi le pourcentage et l'icône sont dans la même case ?
Note on A37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Est-ce qu'on peut traduire en anglais ? Et mettre la légende au début du document ?
Note on F37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Elle est terminée cette légende ?

## _56F9DC9755BA473782653E2940F9 (hidden)
v2ypkt1ONEy--iHCkXYUr6AOQJL0mMRNm-ZVW0VQtilUOVYxOUFQQ0JCTk5CTEVKUk44SVJOUlVVMSQlQCN0PWcu
Form1
{e6c90a5a-49ba-442b-a812-d8ef7f10068b}

## Form1
ID | Responsible | Accountable | Support | Consulted | Informed
Requirements review | Olivier Chantaseng |  | Mohamed Mhamo | Etienne Bernouli
Risk analysis / Assessement | Atif Satif |  | Elisa Fauci
Big Case estimation | Etienne Bernouli
ROI
Blueprint | Dyhia Amour
Org Chart | Dyhia Amour |  | Samira Mhamsa
Feasibility study | Elisa Fauci |  | Dyhia Amour | Fanta Gaby
Authorization matrix
Business Process Website
Customizing guide
Business Process Quote To Cash
Business Process Order To Cash
Business Process KPI
End User Guide
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Est-ce qu'on peut mettre un titre et une description de ce document ?