## Slide 1: List of deliverables
Responsible of Document: Fanta GABY
Author: Fanta GABY, //2023 Validation:
Last update:
Proofread: //2023

## Slide 2: Progress agreement convention
Progress in % | Description | Responsible for validation
0% | Not started yet or insignificant progress | Consultant itself
25% | In progress | Consultant itself
50% | Advanced progress | Task referent
75% | 1st validation proposal | Project Manager Officer
100% | Final validation | Project director

## Slide 3: Deliverables snapshot: preparation (1/4)
Deliverables | Who | Status | Version | Comments
Requirements review | Olivier Chanthaseng | 100% | V1.1 | Validated
Scoping Note | Elisa Fauci | 100% | V1 | Validated
Big case estimation / ROI | Etienne Bernouli | 100% | V1.0 | Validated
Macro-Planning | Samira Mhamsa | 100% | V1 | Validated
Feasibility Study | Elisa Fauci/Dyhia Amour | 100% | V1.0 | Validated
Org Chart | Dyhia Amour | 100% | V1 | Validated
Blueprint | Dyhia Amour | 100% | V1.0 | Validated

## Slide 4: Deliverables snapshot: design (2/4)
Deliverables | Who | Status | Version | Comment
Product Sheets Mock-Up | Etienne Bernouli | 100% | V1.1 | Validated
Information System Mapping | Etienne Bernouli | 100% | V0.1 | Validated
Website Mock-up | Fanta Gaby | 100% | V0.1 | Validated
Business Process Lead to Opportunity | Mohamed Mhamo | 100% | V0.1 | Validated
Business Process Mailing Campaign | Olivier Chantaseng | 100% | V0.1 | Validated

## Slide 5: Deliverables snapshot: design suite (2/4)
Deliverables | Who | Status | Version | Comment
Business Process Opportunity to Customer | Etienne Bernouli, Elisa Fauci | 100 % | V1 | Validated
Business Process Sales to Service | Fanta Gaby, Dyhia Amour, Atif Satif | 100% | V1 | Validated
Authorization Matrix | Etienne Bernouli, Dyhia Amour | 100% | V1 | Validated
MCD Creation | Atif Satif, Mohamed Mhamsa, Etienne Bernouli | 100% | V1 | Validated

## Slide 6: Deliverables snapshot: build (3/3)
Deliverables | Who | Status | Version | Comment
Customizing guide Salesforce | Dyhia Amour | 50% | V0.1 | Advanced pro-gress
Customizing guide Woocommerce | Elisa Fauci | 100% | V1 | Validated
Customizing guide Brevo | Dyhia Amour Olivier Chanthaseng | 100% | V1 | Validated
Customizing guide Power-Automate | Fanta Gaby Samira Mhamsa Mohamed Mhamo | 50% | V0.1 | Advanced pro-gress
End users guide SalesForce | Dyhia Amour Olivier Chanthaseng | 50% | V0.1 | Advanced pro-gress
End users guide Woo-Commerce | Elisa FAUCI | 100% | V1 | Validated
End users guide Brevo | Dyhia Amour Olivier Chanthaseng | 100% | V1 | Validated

## Slide 7: RASIC
ID | Responsible | Accountable | Support | Consulted | Informed
Architecture Mapping | Etienne Bernouli |  |  |  | 
Business Process Customer Journey | Dyhia Amour |  | Etienne Bernouli |  | 
Business Process Website Mock Up |  |  |  |  | 
Business Process Q2C (SAP) |  |  |  |  | 
Business Process O2C |  |  |  |  | 
Customizing Guide Salesforce | Samira Mhamsa |  | Dyhia Amour |  | 
End User Guide | Atif Satif |  | Samira Mhamsa, Dyhia Amour |  |