## Risk Matrix
SIGMA 360 PROJECT
Responsible of Document: Atif SATIF
Author: Atif SATIF, Elisa FAUCI 06/09/2023
Validation:
Last update: Atif SATIF, 27/09/2023
Proofread: Elisa FAUCI
Probability: the risk apparition frequency.
P | Probability | Definition
1 | Very rare | 1 every 5 years
2 | Rare | 1 every year
3 | Uncommon | 1 every 3 months
4 | Frequent | 1 every weeks
Gravity: measuring the effects on incident's targets (more or less important consequences).
G | Gravity | Definition
1 | Minor | Limited consequences
2 | Significative | Visible damages
3 | Major | Important damages
4 | Critical | Irreversible damages
Criticality : Impact of gravity and frequency on the project
C | Criticality
1 | Weak
2 | Moderate
3 | High
4 | Extreme
Calculation of criticality
Probability x Gravity = Criticality
1 => 4 | Weak
5 => 8 | Moderate
9 => 12 | High
13 => 16 | Extreme
ID | Type of risk | Description | Origin of risk | Risk consequences | Probability | Gravity | Criticality | Challenges | Risk mitigation
R1 | Communication | Neglect of external projects, lack of communication between different departments. No effective communication : the usability and timeliness of information that is either created or summarized by an application system.is the risk associated with not getting "the right data/information to the right person/process/system at the right time to allow the right action to be taken." | Non-effective communication with relative stakeholders within the organizations we work with. | Lack of consistency between projects within the same organization. Collusions between projects. Confusion in messages to stakeholders. | 1 | 3 | 3 | External | Be aware of other ongoing projects, communicate the guidelines of our project to other project's managers and make every relevant person pay attention to the stakes of our project, and ourselves aware of other relevant projects.
R2 | Financial | Dwindling cash (Reduction in available cash). | Inadequate budgeting: If the implementation is not properly budgeted, it can lead to dwindling cash. This can happen if the costs of the implementation are underestimated or if there are unexpected expenses. Changes in the scope of the project: If the scope of the project changes, it can lead to dwindling cash. This can happen if the project is expanded or if there are unforeseen challenges that need to be addressed. Delays in the implementation: If the implementation is delayed, it can lead to dwindling cash. This can happen if there are problems with the vendor, if there are changes in the requirements, or if there are other unforeseen challenges. Increased costs: There are other factors that can lead to dwindling cash, such as increased costs for training, support, or maintenance. | Inability to complete the implementation: If the project runs out of cash, it may not be possible to complete the implementation. This can have a negative impact on the organization, as it may not be able to realize the benefits of the Salesforce solution. Loss of momentum: If the implementation is delayed or halted, it can lose momentum. This can make it difficult to get back on track and can lead to further delays and cost overruns. Damage to reputation: If the implementation is not successful, it can damage the organization's reputation. This can make it difficult to attract new customers or partners and can lead to lost business. Financial hardship: If the project runs out of cash, it can put the organization in financial hardship. This can lead to layoffs, salary cuts, or even bankruptcy. | 1 | 4 | 4 | External | Paying attention to the use of the ressources, cost controlling.
R3 | Human | Lack/wrong input on the timesheet. | Too much pressure to end specific tasks so workers will prioritize the deliverables to time recording. The manager forget about keeping the timesheet update. | Poor cost controlling, misevaluation of the project resources availables at a given time. Risk of failure if budget reevaluation in case of a prokect's delay. | 3 | 3 | 9 | Internal | HR team/PMO will verify timesheets. Asking consultants to take 5mn before the end of the work day, even if it is a rush session.
R4 | Human | Unavailability of cross-functional stakeholders | Poor organization, anticipation, and planification of meeting with cross-functional stakeholders. Lack of project's overview, working with heads in the sand. | Project is delayed, sub-optimization of worker's time and resources. Waste of resources and money. | 1 | 3 | 3 | External | Staying aware of stakeholders' availability, anticipating our needs for their presence and planning meetings according to their minimum booking time.
R5 | Human | Unevenly distributed workload | Inadequate planning: If the workload is not properly planned, it can lead to uneven distribution. This can happen if the workload is not evenly divided among the users or if the users are not properly trained on how to use the system. Unrealistic expectations: If the users have unrealistic expectations about the system, it can lead to uneven distribution. This can happen if the users expect the system to do more than it is capable of doing or if they do not understand how to use the system properly. Insufficient resources: If there are not enough resources available to support the workload, it can lead to uneven distribution. This can happen if there are not enough users, not enough computers, or not enough training. Technical problems: Technical problems can also lead to uneven distribution. This can happen if the system is not properly configured or if there are hardware or software problems. | delay project | 3 | 3 | 9 | Internal | PMO will verify workload have been distributed evenly
R6 | Human | Poor division of labour according to competencies | Poor knowledge of the profile of team members, wrong evaluation | Longer project progress and with potentially more errors | 3 | 2 | 6 | Internal | PMO/Project Manager will assign the work based on the competences
R7 | Human | Lack of Implication of key-users on the project | Lack of communication: Key users may not be kept informed about the progress of the implementation or about the changes that are being made to the system. Unrealistic expectations: Key users may have unrealistic expectations about the capabilities of the system or about the time and resources that will be required for the implementation. Lack of trust: Key users may not trust the implementation team or the vendor. Fear of change: Key users may be resistant to change and may not be willing to adopt a new system. Lack of training: Key users may not be adequately trained on how to use the system. Lack of empowerment: Key users may not feel empowered to participate in the implementation process. | Poor adoption: Key users may be reluctant to adopt the new system, which can lead to low adoption rates and poor usage of the system. Resistance to change: Key users may resist change, which can lead to delays and problems during the implementation. Technical problems: Key users may not be able to troubleshoot problems with the system, which can lead to downtime and productivity losses. Poor user experience: Key users may not be happy with the user experience, which can lead to dissatisfaction and low productivity. Failure of the implementation: In severe cases, the lack of implication of key-users can lead to the failure of the implementation. | 1 | 3 | 3 | Internal | Having good relationship with the key users
R8 | Legal | Non-respect of documents internal approbation procedure | poor writing or understanding | difficulty in identifying the document | 1 | 4 | 4 | Internal | Authentication of documents
R9 | Financial | Additional cost of overruns (Coût supplémentaire des dépassements) | wrong budget forecast | profit less than the load | 3 | 3 | 9 | Internal | Dedicated cost controllers to check the cost of overruns
R10 | Financial | Project hours tracking | input error or delay | poor project cost assessment | 4 | 1 | 4 | Internal | HR team/PMO will verify timesheets
R11 | Human | Absenteism due to overwork | poor segregation of duties or poor workload assessment | project shutdown, delay | 2 | 4 | 8 | Internal | PMO will verify workload and competences of consultants
R12 | Human | Unplanned leaves | illness, death | delay project | 1 | 4 | 4 | Internal | Social management, not to overload employees with work
R13 | Human | lack of commitment to the project among workforce | lack of person in charge of this task | delay project | 2 | 3 | 6 | Internal | Social management, detecting in advance the level of potential investment of people
R14 | Human | Adapting to the new technologies - end users : Poorly anticipated organizational changes - The arrival of CRM can impact certain roles, processes and decision-making circuits. These changes need to be anticipated and supported. | resistance to change and whole modifications | non-acceptance of the solution | 1 | 4 | 4 | Internal | Efficient training to be provided to the end users on the new technologies
R15 | Partners and subcontractors | Delay in Material reception | poor choice of supplier | delay in delivery of project to customer | 2 | 4 | 8 | External | Dedicated officer assigned for this task and planning in advance
R16 | Partners and subcontractors | "Fait du prince " | natural disaster | delay in delivery of project to customer | 1 | 4 | 4 | External | Follow environnemental circumstances
R17 | Human | Unavailability of end users during UAT | poor planning | uat test backlog | 2 | 4 | 8 | Internal | Having a backup plan: planning extra users
R18 | Human | Unavailability of key users during test | poor planning | uat test backlog | 1 | 2 | 2 | Internal | Having a backup plan: planning extra users
R19 | Human | Inadequate training for the client | Poor training planning Lack of resources Lack of user motivation | Inefficient use of the Salesforce solution Increased support costs A loss of confidence | 1 | 1 | 1 | Internal
R20 | Legal / Quality | Non respect of contract terms (delay of delivery, Quality of service, terms of payment) lead to legal issues | Delay in delivery: This can happen due to unforeseen circumstances, such as natural disasters or labor strikes. However, it can also be due to poor planning or lack of communication between the parties involved. Poor quality of service: This can happen if the service provider does not have the necessary skills or experience, or if they do not follow the agreed-upon standards. Non-payment: This can happen if the customer does not have the funds to pay, or if they are unhappy with the service they have received. | Legal action: If one party breaches the contract, the other party may take legal action. This could result in damages, or even the termination of the contract. Damage to reputation: A breach of contract can damage the reputation of both parties involved. This could make it difficult to get future business. Financial loss: A breach of contract can lead to financial loss for both parties involved. This could include lost profits, legal fees, and other expenses. Damage to relationships: A breach of contract can damage the relationships between the parties involved. This could make it difficult to work together in the future. | 1 | 4 | 4 | Internal | Scope meetings (sprint: regular deliverable )
R21 | Technical and material means | Error or failure during the update | Incompatible software: If the update is not compatible with the software that is currently installed, it may fail. Corrupted files: If the update files are corrupted, they may not be able to be installed correctly. Insufficient disk space: If there is not enough disk space available, the update may not be able to be installed. Power outage: If there is a power outage during the update, it may be interrupted and fail. Human error: If the update is not installed correctly, it may fail. | Data loss: If the update fails, it may cause data loss. System instability: If the update fails, it may make the system unstable and cause other problems. Security vulnerabilities: If the update fails, it may leave the system vulnerable to security attacks. | 1 | 4 | 4 | Internal | Data backup
R22 | Quality | Unavailability of end-users during the test phase | Scheduling conflicts: End-users may be unavailable during the test phase due to scheduling conflicts with other work commitments. Lack of interest: End-users may not be interested in participating in the test phase, either because they do not see the value in it or because they are too busy with other tasks. Fear of change: End-users may be afraid of change and may not want to participate in the test phase because they are worried about how the changes will affect their work. Technical difficulties: End-users may not be able to participate in the test phase due to technical difficulties, such as not having the necessary access or equipment. | Delayed testing: If end-users are unavailable, the testing phase may be delayed, which can lead to delays in the release of the product or service. Incomplete testing: If end-users are not available to test all of the features or functionality of the product or service, the testing may be incomplete, which can lead to problems being discovered after the product or service is released. Negative feedback: If end-users are not available to test the product or service, they may not be able to provide feedback on the usability or functionality of the product or service, which can lead to negative feedback after the product or service is released. | 1 | 3 | 3 | Internal | Having a backup plan: Pplanning extra users