## Risk Matrix
SIGMA 360 PROJECT |  | 360-SAF-RISK_MATRIX-23Q3-TEAM-V1
Responsible of Document : Atif SATIF
Author : Atif SATIF 01/09/2023
Last Update : Atif SATIF 28/09/2023, Etienne BERNOULI 28/09/2023
Last Proofread : Etienne Bernouli 28/09/2023
Validation : Etienne Bernouli 28/09/2023
Probability: the frequency of occurrence of this risk
P | Probability | Definition
1 | Very rare | Probably won't happen
2 | Rare | Unlikely to occur
3 | Uncommon | too likely to occur
4 | Frequent | Will certainly happen
Gravity: measuring the effects on incident's targets (more or less important consequences).
G | Gravity | Definition
1 | Minor | Limited consequences
2 | Significative | Visible damages
3 | Major | Important damages
4 | Critical | Irreversible damages
Detectability : the operational capacity of any organisational system to detect incoming risk.
D | Detectability | Definition
1 | Weak | The risk will be easily detected thanks to the controls.
2 | Moderate | There is a possibility that the risk will be detected with the controls in place.
3 | High | Controls will have difficulty detecting the risk.
4 | Extreme | No chance of detecting the risk, even with controls
Criticality : Impact of gravity and frequency on the project
C | Criticality | Definition
1 | Weak | The impact is negligible and the situation is under control.
2 | Moderate | The impact is limited and the situation needs to be monitored.
3 | High | The impact is significant and the situation gives cause for concern.
4 | Extreme | The impact is critical/catastrophic and the situation is alarming.
Calculation of criticality
Probability x Gravity x Detectability = Criticality
1 => 4 | Weak
5 => 8 | Moderate
9 => 12 | High
13 => 16 | Extreme
Here is a rewording of the sentence: All the comments presented were made by Lionel Rinaldi, who holds the position of quality expert within our organisation.
ID | Type of risk | Description | Origin of risk | Risk consequences | Probability | Detectability | Gravity | Criticality | Person who identified the risk | Person responsible for risk monitoring | Challenges | Risk mitigation
R1 | Communication | Neglect of external projects, lack of communication between different departments. No effective communication : the usability and timeliness of information that is either created or summarized by an application system.is the risk associated with not getting "the right data/information to the right person/process/system at the right time to allow the right action to be taken." | Non-effective communication with relative stakeholders within the organizations we work with. | Lack of consistency between projects within the same organization. Collusions between projects. Confusion in messages to stakeholders. | 1 | 1 | 3 | 3 | Etienne | Etienne (PMO) | External | Be aware of other ongoing projects, communicate the guidelines of our project to other project's managers and make every relevant person pay attention to the stakes of our project, and ourselves aware of other relevant projects.
R2 | Financial | Dwindling cash (Reduction in available cash). | Inadequate budgeting: If the implementation is not properly budgeted, it can lead to dwindling cash. This can happen if the costs of the implementation are underestimated or if there are unexpected expenses. Changes in the scope of the project: If the scope of the project changes, it can lead to dwindling cash. This can happen if the project is expanded or if there are unforeseen challenges that need to be addressed. Delays in the implementation: If the implementation is delayed, it can lead to dwindling cash. This can happen if there are problems with the vendor, if there are changes in the requirements, or if there are other unforeseen challenges. Increased costs: There are other factors that can lead to dwindling cash, such as increased costs for training, support, or maintenance. | Inability to complete the implementation: If the project runs out of cash, it may not be possible to complete the implementation. This can have a negative impact on the organization, as it may not be able to realize the benefits of the Salesforce solution. Loss of momentum: If the implementation is delayed or halted, it can lose momentum. This can make it difficult to get back on track and can lead to further delays and cost overruns. Damage to reputation: If the implementation is not successful, it can damage the organization's reputation. This can make it difficult to attract new customers or partners and can lead to lost business. Financial hardship: If the project runs out of cash, it can put the organization in financial hardship. This can lead to layoffs, salary cuts, or even bankruptcy. | 1 | 2 | 4 | 8 | Atif (QE) | Etienne (PMO) | External | Paying attention to the use of the ressources, cost controlling.
R3 | Human | Lack/wrong input on the timesheet. | Too much pressure to end specific tasks so workers will prioritize the deliverables to time recording. The manager forget about keeping the timesheet update. | Poor cost controlling, misevaluation of the project resources availables at a given time. Risk of failure if budget reevaluation in case of a prokect's delay. | 3 | 1 | 3 | 9 | Atif (QE) | Etienne (PMO) | Internal | HR team/PMO will verify timesheets. Asking consultants to take 5mn before the end of the work day, even if it is a rush session.
R4 | Human | Unavailability of cross-functional stakeholders | Poor organization, anticipation, and planification of meeting with cross-functional stakeholders. Lack of project's overview, working with heads in the sand. | Project is delayed, sub-optimization of worker's time and resources. Waste of resources and money. | 1 | 1 | 3 | 3 | Etienne | Etienne (PMO) | External | Staying aware of stakeholders' availability, anticipating our needs for their presence and planning meetings according to their minimum booking time.
R5 | Human | Unevenly distributed workload | Inadequate planning: If the workload is not properly planned, it can lead to uneven distribution. This can happen if the workload is not evenly divided among the users or if the users are not properly trained on how to use the system. Unrealistic expectations: If the users have unrealistic expectations about the system, it can lead to uneven distribution. This can happen if the users expect the system to do more than it is capable of doing or if they do not understand how to use the system properly. Insufficient resources: If there are not enough resources available to support the workload, it can lead to uneven distribution. This can happen if there are not enough users, not enough computers, or not enough training. Technical problems: Technical problems can also lead to uneven distribution. This can happen if the system is not properly configured or if there are hardware or software problems. | delay project | 3 | 1 | 3 | 9 | Atif (QE) | Etienne (PMO) | Internal | PMO will verify workload have been distributed evenly
R6 | Human | Poor division of labour according to competencies | Poor knowledge of the profile of team members, wrong evaluation | Longer project progress and with potentially more errors | 3 | 1 | 2 | 6 | Atif (QE) | Etienne (PMO) | Internal | PMO/Project Manager will assign the work based on the competences
R7 | Human | Lack of Implication of key-users on the project | Lack of communication: Key users may not be kept informed about the progress of the implementation or about the changes that are being made to the system. Unrealistic expectations: Key users may have unrealistic expectations about the capabilities of the system or about the time and resources that will be required for the implementation. Lack of trust: Key users may not trust the implementation team or the vendor. Fear of change: Key users may be resistant to change and may not be willing to adopt a new system. Lack of training: Key users may not be adequately trained on how to use the system. Lack of empowerment: Key users may not feel empowered to participate in the implementation process. | Poor adoption: Key users may be reluctant to adopt the new system, which can lead to low adoption rates and poor usage of the system. Resistance to change: Key users may resist change, which can lead to delays and problems during the implementation. Technical problems: Key users may not be able to troubleshoot problems with the system, which can lead to downtime and productivity losses. Poor user experience: Key users may not be happy with the user experience, which can lead to dissatisfaction and low productivity. Failure of the implementation: In severe cases, the lack of implication of key-users can lead to the failure of the implementation. | 1 | 1 | 3 | 3 | Atif (QE) | Etienne (PMO) | Internal | Having good relationship with the key users
R8 | Legal | Non-respect of documents internal approbation procedure | poor writing or understanding | difficulty in identifying the document | 1 | 1 | 4 | 4 | Atif (QE) | Samira (GED) | Internal | Authentication of documents
R9 | Financial | Additional cost of overruns (excess spending) | wrong budget forecast | profit less than the load | 3 | 1 | 3 | 9 | Atif (QE) | Etienne (PMO) | Internal | Dedicated cost controllers to check the cost of overruns
R10 | Financial | Project hours tracking | input error or delay | poor project cost assessment | 4 | 1 | 1 | 4 | Atif (QE) | Etienne (PMO) | Internal | HR team/PMO will verify timesheets
R11 | Human | Absenteism due to overwork | poor segregation of duties or poor workload assessment | project shutdown, delay | 2 | 1 | 4 | 8 | Atif (QE) | Etienne (PMO | Internal | PMO will verify workload and competences of consultants
R12 | Human | Unplanned leaves | illness, death | delay project | 1 | 1 | 4 | 4 | Atif (QE) | Etienne (PMO) | Internal | Social management, not to overload employees with work
R13 | Human | lack of commitment to the project among workforce | lack of person in charge of this task | delay project | 2 | 1 | 3 | 6 | Atif (QE) | Etienne (PMO) | Internal | Social management, detecting in advance the level of potential investment of people
R14 | Human | Adapting to the new technologies - end users : Poorly anticipated organizational changes - The arrival of CRM can impact certain roles, processes and decision-making circuits. These changes need to be anticipated and supported. | resistance to change and whole modifications | non-acceptance of the solution | 1 | 1 | 4 | 4 | Atif (QE) | Elisa (CM) | Internal | Efficient training to be provided to the end users on the new technologies
R15 | Partners and subcontractors | Delay in Material reception | poor choice of supplier | delay in delivery of project to customer | 2 | 1 | 4 | 8 | Atif (QE) | Mohamed (TE) | External | Dedicated officer assigned for this task and planning in advance
R16 | Partners and subcontractors | "Fait du prince " | natural disaster | delay in delivery of project to customer | 1 | 1 | 4 | 4 | Atif (QE) | Atif (QE) | External | Follow environnemental circumstances
R17 | Human | Unavailability of end users during UAT | poor planning | uat test backlog | 2 | 1 | 4 | 8 | Atif (QE) | Etienne (PMO) | Internal | Having a backup plan: planning extra users
R18 | Human | Unavailability of key users during test | poor planning | uat test backlog | 1 | 1 | 2 | 2 | Atif (QE) | Etienne (PMO) | Internal | Having a backup plan: planning extra users
R19 | Human | Inadequate training for the client | Poor training planning Lack of resources Lack of user motivation | Inefficient use of the Salesforce solution Increased support costs A loss of confidence | 1 | 1 | 1 | 1 | Atif (QE) | Olivier (TE) | Internal
R20 | Legal / Quality | Non respect of contract terms (delay of delivery, Quality of service, terms of payment) lead to legal issues | Delay in delivery: This can happen due to unforeseen circumstances, such as natural disasters or labor strikes. However, it can also be due to poor planning or lack of communication between the parties involved. Poor quality of service: This can happen if the service provider does not have the necessary skills or experience, or if they do not follow the agreed-upon standards. Non-payment: This can happen if the customer does not have the funds to pay, or if they are unhappy with the service they have received. | Legal action: If one party breaches the contract, the other party may take legal action. This could result in damages, or even the termination of the contract. Damage to reputation: A breach of contract can damage the reputation of both parties involved. This could make it difficult to get future business. Financial loss: A breach of contract can lead to financial loss for both parties involved. This could include lost profits, legal fees, and other expenses. Damage to relationships: A breach of contract can damage the relationships between the parties involved. This could make it difficult to work together in the future. | 1 | 1 | 4 | 4 | Atif (QE) | Elisa (CM) | Internal | Scope meetings (sprint: regular deliverable )
R21 | Technical and material means | Error or failure during the update | Incompatible software: If the update is not compatible with the software that is currently installed, it may fail. Corrupted files: If the update files are corrupted, they may not be able to be installed correctly. Insufficient disk space: If there is not enough disk space available, the update may not be able to be installed. Power outage: If there is a power outage during the update, it may be interrupted and fail. Human error: If the update is not installed correctly, it may fail. | Data loss: If the update fails, it may cause data loss. System instability: If the update fails, it may make the system unstable and cause other problems. Security vulnerabilities: If the update fails, it may leave the system vulnerable to security attacks. | 1 | 1 | 4 | 4 | Atif (QE) | Mohamed (TE) | Internal | Data backup
R22 | Quality | Unavailability of end-users during the test phase | Scheduling conflicts: End-users may be unavailable during the test phase due to scheduling conflicts with other work commitments. Lack of interest: End-users may not be interested in participating in the test phase, either because they do not see the value in it or because they are too busy with other tasks. Fear of change: End-users may be afraid of change and may not want to participate in the test phase because they are worried about how the changes will affect their work. Technical difficulties: End-users may not be able to participate in the test phase due to technical difficulties, such as not having the necessary access or equipment. | Delayed testing: If end-users are unavailable, the testing phase may be delayed, which can lead to delays in the release of the product or service. Incomplete testing: If end-users are not available to test all of the features or functionality of the product or service, the testing may be incomplete, which can lead to problems being discovered after the product or service is released. Negative feedback: If end-users are not available to test the product or service, they may not be able to provide feedback on the usability or functionality of the product or service, which can lead to negative feedback after the product or service is released. | 1 | 1 | 3 | 3 | Atif (QE) | Elisa (CM) | Internal | Having a backup plan: Pplanning extra users
Note on B2: Ce document n'a pas d'indentifiant, il n'est pas daté, pas établi (c'est-à-dire rédigé, vérifié, approuvé). Correspond-il à la charte graphique de l'entreprise (ce n'est plus un document de travail mais un document d'activité au sens de l'ISO 15489-1). Il convient également de définir le mode de suivi des risques, par qui, etc., autrement dit, de procédurer son utilisation. Voir la codification avec le gestionnaire documentaire
Note on B18: Utilisateur: Préciser davantage ce que l'on entend dans les définitions. Par exemple, les conséquences importantes doivent être caractérisées (impossibilité pour l'utilisateur d'avoir accès à la base de données, perte de connection pendant X temps, etc). Cette échelle ne doit pas être interprétable.
Note on B24: Y-a-t-il une procédure de management du risque qui détaille davantage cette gestion du risque? Note : décrire comment le risque peut être géré (réduit, supprimé), mais aussi transféré. Cf. série des ISO 31000 sur le management du risque et ISO 19600 sur la management de la compliance. dans le l'organisation jusqu'à présent cette procédure n'est pas encore rédigée voir le gestionnaire des doc & PMO
Note on B25: Note : pour établir la criticité, il peut y avoir un trosième critère, qui est la capacité (ou non) à détecter les problèmes. Le 3iem critere
Note on B31: Y-a-t-il une procédure de management du risque qui détaille davantage cette gestion du risque? Note : décrire comment le risque peut être géré (réduit, supprimé), mais aussi transféré. Cf. série des ISO 31000 sur le management du risque et ISO 19600 sur la management de la compliance. dans le l'organisation jusqu'à présent cette procédure n'est pas encore rédigée voir le gestionnaire des doc & PMO
Note on B32: Note : pour établir la criticité, il peut y avoir un trosième critère, qui est la capacité (ou non) à détecter les problèmes. Le 3iem critere
Note on B39: A partir de quelle criticité considère-t-on que le risque est inacceptable et doit faire l'objet d'un traitement?
Note on B43: Qui est en charge de la gestion des risques et de ce fichier? Périodicité de revue?
Note on A47: Pourquoi l'ordre des numéros n'est-il pas un ordre logique?
Note on M47: Il manque des colonnes permettant la mîtrise du risque. En sus de la maîtrise du risque de par les actions existantes, il convient d'ajouter les points suivants : - Actions à mener pour diminuer le risque, - Date de fin prévisionnelle, - % avancement, - Date de clôture de l'action, - Efficacité de l'action et mesure d'efficacité. Si l'action menée n'est pas efficace, une nouvelle action doit être menée et tracée.
Note on C48: 'Manque de communication" et "Pas de communication" ne sont-ils pas deux risques différents? Leurs impacts et leur criticiité n'est-elle pas différente? A méditer.
Note on E48: Quelles peuvent être les conséquences financières pour l'organisation?
Note on M48: Ne pas oublier que le projet vit et que si des risques sont maîtrisés ou disparaissent, d'autres évoluent ou apparaissent. Il conviendrait d'ajouter au document une page servant de notice d'utilisation et précisant notamment ces points.
Note on E49: Risque juridique?
Note on M49: Détailler : les risques financiers sont également maîtrisés en amont du cost control par la tenue du planning, ce qui permet d'éviter les dérives. Pour ce qui concerne les ressources, elles doivent être ad"quates si l'on veut éviter les dérives de planning. Il y a donc un recensement via la matrice des compétences. Si le périmètre du projet change, il est nécessaire d'établir des avenants afin de maîtriser l'aspect financier. Cf. Rôle du PMO en appui du Chef de Projet. Pour rappel, le Chef de Projet conduit le projet, le PMO est en chage de la gestion contractuelle.
Note on D50: Ne pas oublier le problème principal qui est la rigueur / l'absence de contrôle croisé.
Note on M50: Cela rentre dans la définition des rites de management, qui doivent être précisés dans le planq ualité du projet. Définir dans la matrice des compétences la focntion de vérification et celle de validation. Passe également par une planification journalière des tâches par le Chef de Projet.
Note on E52: Impacts financiers, juridiques, etc.?
Note on I52: Que fait-on pour réduire ce risque?
Note on M52: Il manque les points suivants : - Etablissement d'un planning, - Suivi du planning et des dérives éventuelles, - Mise en place d'une procédure de respect des délais, - Information du client en cas de retard et permutation de certaines opérations afin de limiter l'impact sur le délai, en accord avec le client si requis, - Le cas échéant, ouverture d'une fiche d'écart et utilisation du REX suite à traitement des actions, - Affectaction de ressources adéquates et compétences, critères de sélection selon matrice de coméptences, - etc.
Note on AB52: Que fait-on pour réduire ce risque?
Note on M53: - Matrice des compéténces. - Organigramme avec définition des postes clés du projet et des redondances (= back-up). - Organisation du planning et des congés (qui valide les CP / qui est présent, qui est absent, etc.).
Note on M54: - Ecoute du besoin. - Mise en place de réunions (techniques, suivi, etc.). - Formations nécessaires? Avoir de bonnes relations n'est pas une action suffisante en soi pour maîtriser le risque, c'est trop abscons.
Note on M55: - Mise en place d'une procédure de maîtrise des informations documentées : du besoin en création à la destruction des documents, définition de l'identification et de l'indiçage. Définition des rédacteurs, vérificateurs, approbateurs. - Sensibilisation des équipes au respect des dispositions de cette procédure. - Mesure de l'impact RGPD (à développer).
Note on I56: Que fait-on pour réduire ce risque?
Note on M56: Et en amont, établissement et vérification du budget. Passage en Comité pour validation.
Note on AB56: Que fait-on pour réduire ce risque?
Note on C57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is it different from "R3 lack/wrong input on the timesheet" ?
Note on M57: - Suivi financier mensuel du projet. Comparaison entre les heures consommées et le reste à faire, entre le coefficient de gestion prévisionnel et le réel. - Suivi de la courbe en S afin de mesure la valeur acquise du projet. - Suivi de la VMO (Valorisation Main d'Œuvre). - Alerte sur les dérives du projet si concerné. - Vérification de la ventilation des heures selon les tâches à effectuer afin d'identifier les facteurs de non-productivité et de les traiter.
Note on M58: Dans ce cas, il s'agit plutôt de suivre les équipes dans leur quotidien, d'organiser des morning meetings, etc. L'absentéisme subi est un indicateur de santé au travail. Pour l'absentéisme non subi (congés), la gestion se fait via le planning des congés, la définition des postes clés et des redondances.
Note on M59: Voir plus haut et en cas de départ, ajouter la capacité à recruter pour compenser les départs.
Note on M60: Vori plus haut
Note on M61: Mise en place d'un accompagnement à la gestion du changement. - Définition des supports de formation. - Définition du mode d'accompagenement. - Mesure in fine des résultats obtenus. Ce point doit être valorisé dès l'offre commerciale.
Note on E62: Et financier, juridique, etc. Cela est valable pour un certain nombre de risques mentionnés
Note on L62: CASE J47 : Comment sélectionne-t-on et suit-on les fournisseurs de manière à garantir les délais? Comment informe-t-on les fournisseurs des exigences en termes de délais? Comment évalue-t-on les fournisseurs? Le REX effectué sur projet permet-il d'optimiser le panel, afin d'accroître notre satisfaction et donc celle du client?
Note on M62: C'est le travail du planner. Qui assure cette fonction au sein du projet?
Note on M64: Et si cela a un impact sur le délai contractuel, informer le donneur d'ordres client et ouvrir un constat d'aléa à lui soumettre pour prise en compte des frais de mobilisation /démobilisation des équipes projet.
Note on L65: Ne pas oublier de faire signer le PV d'essai par le client afin d'attester de la conformité aux exigences.
Note on M65: Cf. supra.
Note on M66: -Etablir avec le client son besoin -Définir le programme de formation - Réaliser le support de formation / Faire valider au client - Voir pour prise en compte par les OPCO - Kit formation : support de formation, scenario pédagogique, fiche de présence, test final, évaluation à chaud, évaluation à froid. - Réaliser la formation
Note on E67: Ajouter le risque juridique ppour non-respect des clauses contractuelles. Il y a également le risque que des prestations non prévues initiaielement soient ajoutées par le client au fil du projet.
Note on M67: Pour la réalisation : - Réalisation de la revue des exigences à l'appel d'offres - Réalisation de la revue de commande - Réalisation de la réunion d'enclenchement - Réalisation des réunions de pilotage du projet + réunions techniques - Pour la partie financière : réaliser le suivi mensuel de la facturation - Pour le suivi des avancements : courbe en S et suivi du planning - Pour la qualité : vérification / validation des livrables et des opérations par le Chef de Projet
Note on C69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is it different from R17 and R18?
Note on M69: - Intérêt des utilisateurs : développer l'appétence via les méthodes de gestion du changement mises en œuvre. - Conflits de tâches : gestion du planning. - Tests incomplets : faire un plan de test incluant les essais à réaliser, les fonctionnalités vérifiées, les dates prévisionnelles, etc. Si écart, ouverture d'une fiche de non-conformité avec investigation des causes fondamentales du problème. pour en maîtriser les délais de résolution, lancer une démarche QRQC. - Difficultés techniques : gérer les difficultés techniques par des réunions internes, des réunions avec le client, etc. Formaliser les questions et difficultés pouvant nuire au projet sous la forme d'une main courante, de manière à remonter les attentes/réponses envers le client et faciliter le traitement des actions par le Chef de Projet. - Qualité : éviter les non-qualités par la gestion du planning de réalisation, les vérifications et validations avant essai.
Note on B70: Ne pas oublier le risque de ne pas comprendre les enjeux du projet, dont la maîtrise passe par : - L'écoute client lors de la définition du besoin, - La réalisation de la revue des exigences à l'appel d'offre puis à la commande, - La réalisation de la revue de lancement, - La réalisation de réunions de suivi du projet, technique, etc., soit avec le client, soit au sein de l'équipe projet.
Note on B71: Y-a-t-il un risque lié au déploiement de moyens financiers insuffisants?
Note on B72: Y-a-t-il un risque lié à la protection des données (fuite de données, piratage, etc.)?