## Slide 1: List of deliverables
Responsible of Document: Fanta GABY
Author: Fanta GABY, //2023 Validation:
Last update:
Proofread: //2023

## Slide 2: Progress agreement convention
Progress in % | Description | Responsible for validation
0% | Not started yet or insignificant progress | Consultant itself
25% | In progress | Consultant itself
50% | Advanced progress | Task referent
75% | 1st validation proposal | Project Manager Officer
100% | Final validation | Project director

## Slide 3: Deliverables snapshot (1/4)
Deliverables | Who | Status | Version | Comments
Requirements review | Olivier Chanthaseng | 100% | V1.1 | Validated
Scoping Note | Elisa Fauci | 100% | V1 | Validated
Big case estimation / ROI | Etienne Bernouli | 100% | V1 | Validated
Macro-Planning | Samira Mhamsa | 100% | V1 | Validated
Feasibility Study | Elisa Fauci/Dyhia Amour | 100% | V1 | Validated
Org Chart | Dyhia Amour | 100% | V1 | Validated
Blueprint | Dyhia Amour | 100% | V1.1 | Validated

## Slide 4: Deliverables snapshot (2/4)
Deliverables | Who | Status | Version | Comment
Product Sheets Mock-Up | Etienne Bernouli | 100% | V1.1 | Waiting for second validation
IS Mapping | Etienne Bernouli | 75% | V0.1 | First validation Progress
Website Mock-up | Fanta Gaby | 50% | V0.1 | Advanced pro-gress
Business Process Lead to Opportunity | Mohamed | 75% | V0.1 | First validation Progress
Business Process Mailing Campaign | Olivier Chantaseng | 75% | V0.1 | First Validation progress

## Slide 5: Deliverables snapshot (3/4)
Deliverables | Who | Status | Version | Comment
Business Process Opportunity to Customer | Etienne Bernouli, Elisa Fauci | 75% | V0.1 | First validation progress
Business Process Sales to Service | Fanta Gaby, Dyhia Amour, Atif Satif | 75% | V0.1 | First validation progress
Authorization Matrix | Etienne Bernouli, Dyhia Amour | 75% | V0.1 | First validation progress
Customizing and tests reports |  | 0% | V0.1 | Not started yet
MCD Creation | Atif Satif, Mohamed Mhamsa, Etienne Bernouli | 75% | V0.1 | First validation progress

## Slide 6: Deliverables snapshot (4/4)
Deliverables | Who | Status | Version | Comment
Customizing guide Salesforce | Dyhia Amour | 50% | V0.1 | Advanced pro-gress
Customizing guide Woocommerce | Elisa Fauci | 50% | V0.1 | Advanced pro-gress
KPIs Recuperation Process | Olivier Chantaseng, Dyhia Amour | 25% | V0.1 | In progress
Customizing guide Website |  | 25% | V0.1 | In progress
End users guide |  | 0% | V0.1 | Not started yet
Business Process Salesforce integration |  | 0% | V0.1 | Not started yet
Business process documentation |  | 0% | V0.1 | Not started yet

## Slide 7: RASCI
ID | Responsible | Accountable | Support | Consulted | Informed
Requirements review | Olivier Chantaseng |  | Mohamed Mhamo | Etienne Bernouli | 
Risk analysis/ Assessement | Atif Satif |  | Elisa Fauci |  | 
Big Case estimation | Etienne Bernouli |  |  |  | 
ROI | Collaborative |  |  |  | 
Blueprint | Dyhia Amour |  | Etienne Bernouli |  | 
Org Chart | Dyhia Amour |  | Samira Mhamsa |  | 
Feasibility study | Elisa Fauci |  | Dyhia Amour | Fanta Gaby | 
Products Sheets Mock Up | Fanta Gaby |  | Etienne Bernouli |  | 
Business Progress Mailing Compain |  |  |  |  | 

## Slide 8: RASCI
ID | Responsible | Accountable | Support | Consulted | Informed
Architecture Mapping | Etienne Bernouli |  |  |  | 
Business Process Customer Journey | Dyhia Amour |  | Etienne Bernouli |  | 
Business Process Website Mock Up |  |  |  |  | 
Business Process Q2C (SAP) |  |  |  |  | 
Business Process O2C |  |  |  |  | 
Customizing Guide Salesforce | Samira Mhamsa |  | Dyhia Amour |  | 
End User Guide | Atif Satif |  | Samira Mhamsa, Dyhia Amour |  |