# PROJECT COMPLETION REPORT

SIGMA360 CRM SALESFORCE – TEAM CRM ALPHA

_____________________________________________________________________________

Author: Etienne Bernouli, 05/12/2023
Proofread:

_____________________________________________________________________________

GOAL OF THE DOCUMENT

The goal of this document is to help manage the transfer of the SIGMA360 CRM SALESFORCE project, that was led by the team CRM Alpha, to another project’s team.

This document contains:

- Connection information;

- The description of each important document, its role in the project and the level of accuracy of the document;

- A list of requirements and their level of completion, explaining what has already been done (UAT validation) and what is still to be done.

GLOBAL COMPLETION OF THE PROJECT

The project is ready to GO LIVE but has been simplified. You can compare the IS ARCHITECTURE V1.0 to the POST WORK IS ARCHITECTURE V1.0 to see how the project design evolved through time. 

The project is still in DEV version and is ready to GO LIVE but needs a Pre-Prod phase to make sure that everything is set up correctly before exporting/importing set up and data from DEV to PROD.

CUSTOMIZING GUIDES

All Customizing Guides are not completed.

POWER AUTOMATE (Integration)

The Power Automate Customizing Guide surely is the most important because it explains how the Website and Salesforce are connected and lists the fields mapped together between each software.

BREVO (Mailing Automation)

The Brevo Customizing and End-User Guides are merged in the same document.

WEBSITE (Front-End)

The front-end part of the website is easy to take control of. The use of Elementor Pro plug-in is intuitive.

WEBSITE (Back-End)

The Website/WooCommerce Customizing Guide lists the plug-ins included on the website and the API keys used.

SALESFORCE (CRM)

The Salesforce Customizing Guide only contains the Data Conceptual Matrix, listing the objects and fields used in Salesforce, and accessible via Salesforce > Set Up > Quick Find > Schema Builder.
The Salesforce Customizing guide does not yet contain information on how the Salesforce Set Up responds to the project’s needs. Are missing:

- Which Price Book we use and why,

- Which Profiles we use and why,

- How the Lead Conversion Pipe is customized,

- How we use the Web-to-Lead form.

1.	CONNECTION INFORMATION	1

1.	Website DEV	1

2.	Website PROD	1

3.	Salesforce DEV	1

4.	Salesforce PROD (not created)	1

5.	Power Automate	2

6.	Brevo	2

7.	Google Analytics	2

8.	Publer	2

9.	Google Ads	2

10.	WIKI	2

2.	DOCUMENTATION	2

1.	SCOPING NOTE	3

2.	MACRO PLANNING	3

3.	MARKETING	3

4.	CATALOGUE	3

5.	ISHIKAWA’S DIAGRAM	3

6.	ORGANIGRAM	3

7.	PLANNING & DASHBOARD	3

8.	OPEN PROJECT	3

9.	REQUIREMENTS REVIEW	4

10.	NAMING CONVENTION	4

11.	LIST OF DELIVERABLES	4

12.	RISK MATRIX	4

13.	FEASIBILITY STUDY	4

14.	BLUEPRINT	4

15.	ROI	4

16.	BUSINESS PROCESS	5

17.	IS ARCHITECTURE	5

18.	DATA TRANSFER TABLE	5

19.	QUESTIONS FOR SALESFORCE EXPERT	5

20.	AUTHORIZATIONS MATRIX	6

21.	CUSTOMIZING GUIDES	6

22.	END-USER/TRAINING GUIDES	6

23.	UAT	6

24.	CRM ALPHA STEERING COMMITTEES	6

25.	PROJECT GLOBAL REVIEW	7

26.	PROJECT COMPLETION REPORT	7

3.	COMPLETION OF REQUIREMENTS	7

1.	COMPLETED	8

1. Website front-end (Customer journey)	9

2. Website back-end (Sales Representative experience)	9

3. Salesforce	9

4.	Brevo	10

5.	Website to Salesforce(Integration)	10

Synchronization of Products data	10

Synchronization of Customers data	10

Synchronization of Orders data	10

2.	IN PROGRESS	10

1.	Website front-end	10

2.	Integration	10

1.	Website > Salesforce	10

3.	NOT STARTED	10

1.	Website front-end	10

2.	Website back-end	10

3.	Salesforce	11

4.	Publer	11

5.	Salesforce to Website (Integration)	12

Synchronization of Stock Level data> Issue: no connection with SAP (SAP controls Stock Levels)	12

6.	Salesforce to SAP (Integration)	12

Synchronization of Products data	12

Synchronization of Customers data	12

Synchronization of Orders data	12

7. SAP to Salesforce (Integration)	12

Synchronization of Products data	12

Synchronization of Customers data	12

Synchronization of Orders data	12

Synchronization of Invoices data	12

Synchronization of Stock Level	12

8. SAP to Customer (Integration)	12

9. WordPress to Google Analytics (integration)	13

10. Google Analytics to Salesforce (integration)	13

11. Salesforce to Brevo (integration)	13

12. Brevo to Salesforce (integration)	13

13. Publer to Salesforce (integration)	13

# CONNECTION INFORMATION

## Website DEV

URL front-end: https://sandbox3.ekovya.com
URL back-end: https://sandbox3.ekovya.com/wp-admin
Login: administrator
Password: XXXXXXXXXXX

## Website PROD

URL front-end: Accueil - Store Ekovya 
URL back-end: Tableau de bord ‹ Store Ekovya — WordPress
Login: smm@ekovya.com
Password: XXXXXXXXXXX

## Salesforce DEV

URL: Login | Salesforce
Login: ekovya.dev@ekovya.com
Password: XXXXXXXXXXX

## Salesforce PROD (not created)

URL: 
Login:
Password:

## Power Automate

URL: https://make.powerautomate.com/
Login: power@ekovya.com
Password: XXXXXXXXXXX

## Brevo

URL: Brevo | Suite CRM
Login: smm@ekovya.com
Password: XXXXXXXXXXX

## Google Analytics

URL: Platform Home (google.com)
Login: ekovya.dev@ekovya.com
Password: XXXXXXXXXXX

## Publer (not created)

URL: 
Login:
Password:

## Google Ads

URL: Google Ads | Obtenez des clients et boostez vos ventes grâce à la publicité en ligne
Login: ekovya.dev@ekovya.com
Password: XXXXXXXXXXX

## WIKI

URL: EKOVYA
Login + password: your Microsoft Azure Account

## SQUASH TM

URL: Authentification (ekovya.com)
Login + password: ask your administrator to create your account.

# DOCUMENTATION

Below is the list of the documentation written to follow and monitor the project’s evolution.

## SCOPING NOTE

The first document from the first workshop with the client. Helps understanding the global context of the project, the structure of the client’s organization, and its global strategy. 
S360-SAF-SCOPING_NOTE-23Q3-OPEN-V1.pdf

- MACRO PLANNING

The anticipated planning of the project initially designed. Used to compare the evolution of the project on a given moment to how we thought it would evolve. 
S360-SAF-MACRO PLANNING-23Q3-TEAM-V.1.xlsx

## MARKETING

Contains marketing and benchmark studies on Ekovya’s brand.
03_MARKETING

## CATALOGUE

List of Ekovya’s products
CATALOGUE EKOVYA 2023.pdf

## ISHIKAWA’S DIAGRAM

Define the scope of the project and the resources needed.
S360-SAF-Ishikawa's diagram CRM Alpha-23Q3-OPEN.V1.png

## ORGANIGRAM

Define the organizational structure of the project.
S360-SAF-ORGANIGRAM CRM- 23Q3-OPEN-1 V1.pptx

## PLANNING & DASHBOARD

List of tasks distribution and the documentation created to support the realization and synchronization of these tasks. Includes the comitology (the list of meetings to follow the project’s evolution).
S360-SAF-PLANNING_&_DASHBOARD-23Q3-OPEN-V1.xlsx
/!\ No update on planning since the beginning of UAT the 15th of November 2023.

## OPEN PROJECT

Online software to follow the project’s evolution and track consumption of costs (work hours) and issues (tickets).
https://project.ekovya.com

## REQUIREMENTS REVIEW

List of the client’s requirements based on the workshop “Reception of Needs”.
S360-SAF-REQUIREMENTS REVIEW-23Q4-OPEN-V1.1.pdf

## NAMING CONVENTION

Defines and synchronizes how the documentation should be named to be consistent throughout the project’s evolution.
S360-SAF-NAMING_CONVENTION_SALESFORCE_CRM_ALPHA-23Q3-OPEN.V1.pptx	 
/!\ Another Naming Convention has been edited by the team ERP Bravo (SAP project) at the end of November 2023. Coordinate with the other teams working on digital transformation to update and synchronize the naming convention.

## LIST OF DELIVERABLES

List of software and documentation deliverables, and their state of advancement. 
S360-SAF-LIST OF DELIVERABLES-23Q3-REST-V1.0.pptx

## RISK MATRIX

Assessing the risks of the project and how to mitigate it.
S360-SAF-RISK_MATRIX-23Q3-TEAM-V1.0.xlsx

## FEASIBILITY STUDY

Composed of a Word document explaining the categorization of requirements in 3 priority levels, and an Excel document evaluating the level of difficulty to complete the requirements.
S360-SAF-FEASABILITY STUDY-23Q3-TEAM-V1.0.docx
S360-SAF-FEASIBILITY STUDY-23Q3-OPEN-V1-23Q3-TEAM-V1.0.xlsx

## BLUEPRINT

The most complete explanation of what the project is supposed to be and how the CRM Alpha team is going to deploy the digital solution according to the requirements previously collected and prioritized. 
S360-SAF-BLUEPRINT-23Q4-OPEN-V1.0.pdf

## ROI

Calculate the Return-On-Investment (defined as the profitability threshold). This document includes the evaluation of the Budget – Human and Material resources - and different profitability scenario according to different expected turnover increases.
S360-SAF-ROI-23Q3-TEAM-V1.0.xlsx
/!\ For a virgin model of the Excel document used for calculation, see below: 
S360-SAF-ROI_TOOLS-23Q3-TEAM-V1.0.xlsx

## BUSINESS PROCESS

List of Business Processes. BPs support synchronization to conceptualize the digital solution in the same way as every stakeholder.
/!\ The drawing can be edited in Ekovya’s wiki: Business Process | EKOVYA (Connect > Edit > double-click on picture)
08_BUSINESS PROCESS

## IS ARCHITECTURE

The conceptual architecture of the system. Helps understand how the system is supposed to work. The folder is composed of the first version of the IS Architecture (produced in Design phase), the post-work architecture (the result at the end of the project), and the Salesforce Conceptual Data Matrix (from Design phase).
09_IS ARCHITECTURE

## DATA TRANSFER TABLE

List the fields mapped between the different softwares. Helps design the integration between softwares. 
S360-SAF-WOOCOMMERCE-DATA_TRANSFER_TABLE-OPEN-23Q4-V0.1.xlsx
/!\ Not up to date!

/!\ For better information, see the Automation Flows in Power Automate
S360-CUSTOMIZING GUIDE POWER AUTOMATE-TEAMS-V0.1.docx)

/!\ The document above is not complete. For better information, see the Power Automate interface: 
URL: Microsoft Power Automate | Mes flux
Login: power@ekovya.com

## QUESTIONS FOR SALESFORCE EXPERT

List of technical questions (with related documentation) we asked the Salesforce expert to evolve the project toward completion.
Questions: S360-SAF-QUESTIONS_FOR_EXPERTS-23Q4-TEAM-V0.1.xlsx
Documentation: 17_QUESTIONS FOR SALESFORCE EXPERT

## AUTHORIZATIONS MATRIX

List of requirements relative to data access and security within Salesforce (requirement not complete)
S360-SAF-AUTHORIZATIONS_MATRIX-23Q4-OPEN-V1.0.docx

## CUSTOMIZING GUIDES

Documents explaining how to administrate the solution, how it is designed and how it works. Contains elements of context and warnings about structural integrity of the solution. Very helpful to understand how consultants, administrators, and developers can customize the solution to adapt it to the ever-evolving needs of the company.
12_CUSTOMIZING GUIDE
/!\ The documents are not complete.

## END-USER/TRAINING GUIDES

The training guides are documents that support the training of people who use the solutions (by opposition to the ones who customize it: developers, administrators). The end-user guides are more complete documents which contain all details needed to master the solution as an end-user.
13_END -USER GUIDE -TRAINING 
/!\ The End-user guides and the Trainings guides are much similar and are merge into the End-user guides documentation.
/!\ The documents are not complete.

## UAT

Contains archived list of requirements and how they are validated by User Acceptance Test. 
14_UAT
/!\ Documents not up to date.
/!\ To track the evolution of UAT, go to Squash Test Management (ekovya.com) > SIGMA360 CRM ALPHA > select subfolder SIGMA360 CRM ALPHA > Dashboard > Refresh

## CRM ALPHA STEERING COMMITTEES

Contains CRM Alpha team’s presentations to Pre-Steering Committees, Steering Committees, Directors Boards, and Axe Committees.
15_CRM ALPHA STEERING COMMITTEES
/!\ Order by date: DD/MM/YYYY

## PROJECT GLOBAL REVIEW

An experience review of the project evolution through time, listing the negative points that impacted the project’s progression, and that future project’s team should be aware of, and the positive points that helped beat some rhythm in the project. 
SIG360-SAF-PROJECT_GLOBAL_REVIEW-23Q4-TEAM-V1.0.xlsx

## PROJECT COMPLETION REPORT

This document. Helps the future team to know where the project stopped, what has been achieved and which requirements it could be interesting to take over. 
S360-SAF-PROJECT_COMPLETION_REPORT-23Q4-TEAM-V1.0.docx
/!\ Contains connection information.

# COMPLETION OF REQUIREMENTS

A list of requirements has been created from the conclusion of the workshop “Reception of needs”. Below are listed the requirements that have been completed as expected, the ones still in the build phase and the ones that have not been started.

- SCROLL DOWN TO SEE THE LIST -

🔽

## COMPLETED

### 1. Website front-end (Customer journey)

Customer account creation
Customer login procedure
Add products to cart and see total price
Access to different currencies
Website order payment process
Strong passwords requirements

### 2. Website back-end (Sales Representative experience)

Creation of product sheets
Creation of product categories
Creation of product tags
Applying promotions
Creation of bundles
Creation of cross-selling
Creation of up-selling
Creation of a command order number
Degressive prices relative to quantity of purchase
VAT management

### 3. Salesforce

Log in to Salesforce
Account: creation of a record
Contact: creation of a record
Lead: creation of a record
Opportunity: creation of a record
Orders: creation of a record
Product: creation of a record
Quotes: creation of a record
Campaigns: creation of a record
Task: creation of a record
Creation of users
Send an e-mail
Convert lead to opportunity
Close your deal
Display the number of account creation demands
Profile creation:

- Sales Representative > Assia

- Marketing Manager > Elizabeth

- Sales Director > Elizabeth

- Vice-President > Alexandre

Available connection through mobile phones

### Brevo

Ability to connect to Brevo
Creation of a campaign

### Website to Salesforce	(Integration)

#### Synchronization of Products data

Creation
Update
Delete

#### Synchronization of Customers data

Creation
Update
Delete

#### Synchronization of Orders data

Creation

## IN PROGRESS

## Website front-end

Send a message via a Contact form (to be tested)
Newsletter subscription

### Integration

#### Website > Salesforce

Automatic transfer of Lead data

## NOT STARTED

### Website front-end

Security: 2 factors authentication (Issue: difficulty of setting up WordFence Plug-in)
Display real-time stock-level according to customer privileges (SAP connection issue)
Mail for first contact registration
Thanking mail following a phone call
Follow-up e-mail after cart abandon
Automatic creation of coupons when cart abandon
Customer receives a post-order satisfaction form

### Website back-end

Multilingual: French & English
Calculation of shipping costs
Display cart abandon rate
Display average customer basket 
Price management by customer categories: premium, gold, VIP

### Salesforce

Customized Conversion Pipe:

The steps to convert a lead into an opportunity: must include the account creation as a step to fit the Business Process “Lead to Opportunity”)

Authorizations Matrix:

Sales Rep. profiles access dashboards displaying data they otherwise do not have access to.

Lead assignment rules

> Ekovya’s documentation on sales processes is missing.

### Publer

Set up Publer connection
Accessing Ekovya’s social media accounts

### Salesforce to Website (Integration)

##### Synchronization of Stock Level data
> Issue: no connection with SAP (SAP controls Stock Levels)

### Salesforce to SAP (Integration)

> Issue: no connection with SAP

#### Synchronization of Products data

#### Synchronization of Customers data

#### Synchronization of Orders data

### 7. SAP to Salesforce (Integration)

> Issue: no connection with SAP

#### Synchronization of Products data

#### Synchronization of Customers data

#### Synchronization of Orders data

#### Synchronization of Invoices data

#### Synchronization of Stock Level

### 8. SAP to Customer (Integration)

Send Invoices to Customers

### 9. WordPress to Google Analytics (integration)

Display statistic of visit of each store category
Display visitors’ countries
Display visitors’ average visit time
Display acquisition rate
Display bounce rate

### 10. Google Analytics to Salesforce (integration)

Automatic transfer of data
Allow analysis of website performance

### 11. Salesforce to Brevo (integration)

Transferring e-mail addresses
Organizing e-mail addresses according to scores and criterias

### 12. Brevo to Salesforce (integration)

Transfer data relative to mailing campaign success

### 13. Publer to Salesforce (integration)

Transfer data on social media campaigns performance