## Sheet1
Preparation phase |  |  | Design phase |  |  | Build phase |  |  | Delivery phase
Task | Negative | Positive | Task | Negative | Positive | Task | Negative | Positive | Task | Negative | Positive
OpenProject | Time filling by the team was fairly well controlled, but mainly by the PMOs. Tasks in OpenProject were difficult to plan, as it's hard to get to grips with the software. We think it's important to make sure you've mastered the software before organizing the project. With the exception of the PMOs, the team didn't really get to grips with the tool. After a while, the team stopped entering their hours into OpenProject. We didn't use OpenProject to track task completion. We mainly used Excel to allocate tasks and track deliverables (with Sharepoint links), as this was easier for the team to access. This saved time in ramping up skills. It was difficult to get OpenProject training from the experts. Skills upgrading was mainly handled by the PMOs. OpenProject does not appear to be sufficiently user-friendly (in its free version) to follow the development of a project in a flexible way. On the other hand, it is very useful for managing the project's Days*Human budget, provided that the team regularly fills its working hours. When creating an issue in OpenProject, some experts do not respond to issue notifications. Issue creation is supposed to play the role of an IT support ticket, which we learned two weeks late. Salesforce expert Alain Claude did not respond to OpenProject issues. As an external service provider, we can assume that he is not accustomed to this tool. However, Ekovya's management is very familiar with OpenProject issues management, and this ensures that the project is rigorously monitored by management. | Useful to follow the budget by counting the work hours. | Experts availability | Difficulties in scheduling workshops with the Salesforce expert to increase skills: result -> time wasted designing the solution in a way that was ill-suited to the native functions of the chosen solution (Salesforce). Importance of planning Salesforce workshops at the start of the project, up to and including integration issues. |  | Integration | Loss of time in upgrading Mulesfoft -> lack of budget for the solution. Choice to use Power Automate middleware. Additional budget for plug-ins. Poor knowledge of Salesforce environment (expert unavailable) for integration with Power Automate. |  | UAT |  | Went great. Squaqh TM environment well-organized.
Reception of needs | We didn't ask the customer the right questions. Example: Difficulty in asking for details and clarifying concepts (e.g. a "user-friendly" website). It's important to ask questions that force customers to clarify their expectations. |  | Experts' knowledge | Misuse of the Salesforce expert's knowledge to enhance the design phase -> not available. Lack of expert knowledge of integration issues on the project. | The Wordpress/Woocommerce expert was readily available and knowledgeable on the subject. | SAP | Lack of availability of Alexandre Gain, Vice-President, responsible for Ekovya's SAP customer account -> difficulties in obtaining the computer files needed to connect with Mulesoft -> abandonment of Mulesoft and Salesforce <-> SAP integration project. |  | Documentation Customizing guide & End-user guide | Lack of synchronization and definition of the different guides' objectives.
Deliverables | Getting to grips with them (how they were appropriated, what were the bottlenecks, understanding the role of deliverables in the project). Difficulty to access documents templates, lack of training on the methodolgy needed to produce documention and deliverables: Blueprint & Feasibility study. |  | Business Process | Lack of training in BP design | Draw.io tool for drawing BPs is much efficient
Documentation | Imposition of a specific naming convention for the ERP Bravo team with two weeks to go before the end of the project. -> poor communication between the two teams, particularly on document organization. | Creation of a CRM Alpha naming convention early in the project | Plug-ins | Difficulties in choosing the right plug-ins for Wordpress/Woocommerce to meet the challenges of the project.